## ActivityList AUG23
Project ID | Activity ID | Activity Status | WBS Code | Activity Name | Code [Life Cycle] | Code [Trade] | Performance % | Schedule % | Budgeted Value | Earned Value | Planned Value | Original Duration | Planned Start | Planned Finish | Actual Start | Actual Finish | Start | Finish
PCS_PJ02 | EN.C1.0030 | Completed | OMEGA.UD.[AUG23].EN.C1.ELC | Electrical Equipment Arrangement C1 | EN | EL | 100 | 100 | 0 | 0 | 0 | 8 | 2025-01-01 | 2027-01-24 | 2025-01-03 | 2027-01-24 | 2025-01-03 | 2027-01-21
PCS_PJ02 | CN.C4.0090 | Not Started | OMEGA.UD.[AUG23].CN.C4.ELC | Install Electrical Equipment C4 | CN | EL | 0 | 0 | 7053786.4 | 0 | 0 | 22 | 2025-01-05 | 2027-01-01 | 2025-01-26 | 2027-01-21 | 2025-01-26 | 2027-01-15
PCS_PJ02 | TS.C3.0010 | Not Started | OMEGA.UD.[AUG23].TS.C3.MEC | Mechanical Testing C3 | TS | MC | 0 | 83.33 | 0 | 0 | 0 | 6 | 2025-01-21 | 2027-01-13 | 2025-01-09 | 2027-01-15 | 2025-01-09 | 2027-01-04
PCS_PJ02 | CN.C1.0060 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | Steel Structure C1 | CN | CV | 100 | 100 | 2770579.2 | 2770579.2 | 2770579.2 | 22 | 2025-01-24 | 2027-01-17 | 2025-01-01 | 2027-01-04 | 2025-01-01 | 2027-01-13
PCS_PJ02 | EN.C4.0040 | Completed | OMEGA.UD.[AUG23].EN.C4.CIV | Architectural Drawings C4 | EN | CV | 100 | 100 | 0 | 0 | 0 | 6 | 2025-01-13 | 2027-01-09 | 2025-01-23 | 2027-01-13 | 2025-01-23 | 2027-01-25
PCS_PJ02 | TS.C3.0020 | Not Started | OMEGA.UD.[AUG23].TS.C3.ELC | Electrical Testing C3 | TS | EL | 0 | 0 | 0 | 0 | 0 | 6 | 2025-01-16 | 2027-01-07 | 2025-01-02 | 2027-01-25 | 2025-01-02 | 2027-01-21
PCS_PJ02 | TS.C4.0030 | Not Started | OMEGA.UD.[AUG23].TS.C4.MEP | MEP-E Testing C4 | TS | ME | 0 | 0 | 0 | 0 | 0 | 6 | 2025-01-23 | 2027-01-22 | 2025-01-09 | 2027-01-21 | 2025-01-09 | 2027-02-23
PCS_PJ02 | CN.C3.0100 | Not Started | OMEGA.UD.[AUG23].CN.C3.MEP | Install MEP-E C3 | CN | ME | 0 | 0 | 80050.4 | 0 | 0 | 9 | 2025-02-04 | 2027-02-19 | 2025-02-25 | 2027-02-23 | 2025-02-25 | 2027-02-28
PCS_PJ02 | CN.C1.0080 | Completed | OMEGA.UD.[AUG23].CN.C1.MEC | Install Mechanical Components C1 | CN | MC | 100 | 100 | 9523135.2 | 9523135.2 | 9523135.2 | 30 | 2025-02-21 | 2027-02-28 | 2025-02-10 | 2027-02-28 | 2025-02-10 | 2027-02-13
PCS_PJ02 | MS.C2.0040 | Not Started | OMEGA.UD.[AUG23].MS.ST | C2 Finish |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2025-02-27 | 2027-02-13 | 2025-02-06 | 2027-02-13 | 2025-02-06 | 2027-02-11
PCS_PJ02 | CN.C1.0100 | Not Started | OMEGA.UD.[AUG23].CN.C1.MEP | Install MEP-E C1 | CN | ME | 0 | 100 | 80050.4 | 0 | 80050.4 | 9 | 2025-02-05 | 2027-02-02 | 2025-02-04 | 2027-02-11 | 2025-02-04 | 2027-02-27
PCS_PJ02 | TS.C2.0040 | Not Started | OMEGA.UD.[AUG23].TS.C2.MEP | MEP-M Testing C2 | TS | MM | 0 | 0 | 0 | 0 | 0 | 6 | 2025-02-02 | 2027-02-18 | 2025-02-21 | 2027-02-27 | 2025-02-21 | 2027-02-14
PCS_PJ02 | CN.C2.0060 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | Steel Structure C2 | CN | CV | 100 | 100 | 2770579.2 | 2770579.2 | 2770579.2 | 22 | 2025-02-13 | 2027-02-19 | 2025-02-06 | 2027-02-14 | 2025-02-06 | 2027-02-12
PCS_PJ02 | CN.C4.0070 | Not Started | OMEGA.UD.[AUG23].CN.C4.CIV | Steel Sandwich Panels C4 | CN | CV | 0 | 0 | 816936 | 0 | 0 | 19 | 2025-02-27 | 2027-02-20 | 2025-02-21 | 2027-02-12 | 2025-02-21 | 2027-02-16
PCS_PJ02 | CN.C1.0110 | Not Started | OMEGA.UD.[AUG23].CN.C1.MEP | Install MEP-M C1 | CN | MM | 0 | 100 | 53871.2 | 0 | 53871.2 | 10 | 2025-02-11 | 2027-02-19 | 2025-02-06 | 2027-02-16 | 2025-02-06 | 2027-02-22
PCS_PJ02 | EN.GE.0010 | Completed | OMEGA.UD.[AUG23].EN.GE | Specifications | EN | GR | 100 | 100 | 0 | 0 | 0 | 1 | 2025-02-05 | 2027-02-02 | 2025-02-18 | 2027-02-22 | 2025-02-18 | 2027-02-12
PCS_PJ02 | EN.C4.0010 | Completed | OMEGA.UD.[AUG23].EN.C4.CIV | Boreholes C4 | EN | CV | 100 | 100 | 0 | 0 | 0 | 5 | 2025-02-20 | 2027-02-21 | 2025-02-07 | 2027-02-12 | 2025-02-07 | 2027-03-17
PCS_PJ02 | EN.C4.0020 | Completed | OMEGA.UD.[AUG23].EN.C4.MEC | Mechanical General Arrangement C4 | EN | MC | 100 | 100 | 0 | 0 | 0 | 7 | 2025-03-24 | 2027-03-21 | 2025-03-17 | 2027-03-17 | 2025-03-17 | 2027-03-27
PCS_PJ02 | TS.C2.0010 | Not Started | OMEGA.UD.[AUG23].TS.C2.MEC | Mechanical Testing C2 | TS | MC | 0 | 100 | 0 | 0 | 0 | 6 | 2025-03-14 | 2027-03-15 | 2025-03-20 | 2027-03-27 | 2025-03-20 | 2027-03-15
PCS_PJ02 | EN.GE.0030 | Completed | OMEGA.UD.[AUG23].EN.GE | P&ID | EN | CP | 100 | 100 | 0 | 0 | 0 | 10 | 2025-03-08 | 2027-03-04 | 2025-03-09 | 2027-03-15 | 2025-03-09 | 2027-03-16
PCS_PJ02 | EN.C2.0040 | Completed | OMEGA.UD.[AUG23].EN.C2.CIV | Architectural Drawings C2 | EN | CV | 100 | 100 | 0 | 0 | 0 | 6 | 2025-03-22 | 2027-03-16 | 2025-03-21 | 2027-03-16 | 2025-03-21 | 2027-03-18
PCS_PJ02 | EN.C3.0020 | Completed | OMEGA.UD.[AUG23].EN.C3.MEC | Mechanical General Arrangement C3 | EN | MC | 100 | 100 | 0 | 0 | 0 | 7 | 2025-03-19 | 2027-03-25 | 2025-03-08 | 2027-03-18 | 2025-03-08 | 2027-03-14
PCS_PJ02 | CN.C4.0050 | Completed | OMEGA.UD.[AUG23].CN.C4.CIV | RC SuperStructure C4 | CN | CV | 100 | 100 | 2090938.4 | 2090938.4 | 2090938.4 | 18 | 2025-03-09 | 2027-03-15 | 2025-03-17 | 2027-03-14 | 2025-03-17 | 2027-03-08
PCS_PJ02 | CN.C4.0060 | Not Started | OMEGA.UD.[AUG23].CN.C4.CIV | Steel Structure C4 | CN | CV | 0 | 0 | 2770579.2 | 0 | 0 | 22 | 2025-03-08 | 2027-03-03 | 2025-03-06 | 2027-03-08 | 2025-03-06 | 2027-03-22
PCS_PJ02 | TS.C2.0050 | Not Started | OMEGA.UD.[AUG23].TS.C2.C&P | Control Testing C2 | TS | CP | 0 | 0 | 0 | 0 | 0 | 6 | 2025-03-13 | 2027-03-11 | 2025-03-09 | 2027-03-22 | 2025-03-09 | 2027-03-23
PCS_PJ02 | CN.C2.0020 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | Backfilling C2 | CN | CV | 100 | 100 | 966984.8 | 966984.8 | 966984.8 | 10 | 2025-03-02 | 2027-03-13 | 2025-03-07 | 2027-03-23 | 2025-03-07 | 2027-03-09
PCS_PJ02 | TS.C3.0030 | Not Started | OMEGA.UD.[AUG23].TS.C3.MEP | MEP-E Testing C3 | TS | ME | 0 | 0 | 0 | 0 | 0 | 6 | 2025-03-06 | 2027-03-16 | 2025-03-20 | 2027-03-09 | 2025-03-20 | 2027-04-06
PCS_PJ02 | CN.C3.0030 | Completed | OMEGA.UD.[AUG23].CN.C3.CIV | PC C3 | CN | CV | 100 | 100 | 160052.8 | 160052.8 | 160052.8 | 16 | 2025-04-11 | 2027-04-17 | 2025-04-23 | 2027-04-06 | 2025-04-23 | 2027-04-20
PCS_PJ02 | CN.C2.0090 | Not Started | OMEGA.UD.[AUG23].CN.C2.ELC | Install Electrical Equipment C2 | CN | EL | 0 | 0 | 7053786.4 | 0 | 0 | 22 | 2025-04-08 | 2027-04-05 | 2025-04-04 | 2027-04-20 | 2025-04-04 | 2027-04-06
PCS_PJ02 | CN.C3.0060 | Not Started | OMEGA.UD.[AUG23].CN.C3.CIV | Steel Structure C3 | CN | CV | 0 | 22.73 | 2770579.2 | 0 | 629677.09 | 22 | 2025-04-18 | 2027-04-15 | 2025-04-28 | 2027-04-06 | 2025-04-28 | 2027-04-18
PCS_PJ02 | PC.GE.0020 | Completed | OMEGA.UD.[AUG23].PC | Steel Sandwich Panels | PC | CV | 100 | 100 | 6068664.8 | 6068664.8 | 6068664.8 | 60 | 2025-04-04 | 2027-04-14 | 2025-04-27 | 2027-04-18 | 2025-04-27 | 2027-04-27
PCS_PJ02 | TS.C3.0040 | Not Started | OMEGA.UD.[AUG23].TS.C3.MEP | MEP-M Testing C3 | TS | MM | 0 | 0 | 0 | 0 | 0 | 6 | 2025-04-03 | 2027-04-16 | 2025-04-02 | 2027-04-27 | 2025-04-02 | 2027-04-22
PCS_PJ02 | EN.C2.0020 | Completed | OMEGA.UD.[AUG23].EN.C2.MEC | Mechanical General Arrangement C2 | EN | MC | 100 | 100 | 0 | 0 | 0 | 7 | 2025-04-25 | 2027-04-12 | 2025-04-09 | 2027-04-22 | 2025-04-09 | 2027-04-05
PCS_PJ02 | TS.C4.0040 | Not Started | OMEGA.UD.[AUG23].TS.C4.MEP | MEP-M Testing C4 | TS | MM | 0 | 0 | 0 | 0 | 0 | 6 | 2025-04-28 | 2027-04-15 | 2025-04-03 | 2027-04-05 | 2025-04-03 | 2027-04-05
PCS_PJ02 | TS.C4.0050 | Not Started | OMEGA.UD.[AUG23].TS.C4.C&P | Control Testing C4 | TS | CP | 0 | 0 | 0 | 0 | 0 | 6 | 2025-04-08 | 2027-04-10 | 2025-04-15 | 2027-04-05 | 2025-04-15 | 2027-04-02
PCS_PJ02 | CN.C1.0050 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | RC SuperStructure C1 | CN | CV | 100 | 100 | 2090938.4 | 2090938.4 | 2090938.4 | 18 | 2025-04-08 | 2027-04-09 | 2025-04-28 | 2027-04-02 | 2025-04-28 | 2027-04-17
PCS_PJ02 | CN.C2.0040 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | RC SubStructure C2 | CN | CV | 100 | 100 | 1900625.6 | 1900625.6 | 1900625.6 | 24 | 2025-04-04 | 2027-04-13 | 2025-04-09 | 2027-04-17 | 2025-04-09 | 2027-05-07
PCS_PJ02 | CN.C1.0070 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | Steel Sandwich Panels C1 | CN | CV | 100 | 100 | 816936 | 816936 | 816936 | 19 | 2025-05-01 | 2027-05-01 | 2025-05-22 | 2027-05-07 | 2025-05-22 | 2027-05-09
PCS_PJ02 | CN.C3.0070 | Not Started | OMEGA.UD.[AUG23].CN.C3.CIV | Steel Sandwich Panels C3 | CN | CV | 0 | 0 | 816936 | 0 | 0 | 19 | 2025-05-26 | 2027-05-24 | 2025-05-05 | 2027-05-09 | 2025-05-05 | 2027-05-01
PCS_PJ02 | CN.C3.0050 | Completed | OMEGA.UD.[AUG23].CN.C3.CIV | RC SuperStructure C3 | CN | CV | 100 | 100 | 2090938.4 | 2090938.4 | 2090938.4 | 18 | 2025-05-13 | 2027-05-18 | 2025-05-02 | 2027-05-01 | 2025-05-02 | 2027-05-14
PCS_PJ02 | PC.GE.0010 | Completed | OMEGA.UD.[AUG23].PC | Steel Structure | PC | CV | 100 | 100 | 0 | 20581443.2 | 20581443.2 | 60 | 2025-05-15 | 2027-05-28 | 2025-05-07 | 2027-05-14 | 2025-05-07 | 2027-05-18
PCS_PJ02 | TS.C4.0010 | Not Started | OMEGA.UD.[AUG23].TS.C4.MEC | Mechanical Testing C4 | TS | MC | 0 | 0 | 0 | 0 | 0 | 6 | 2025-05-10 | 2027-05-22 | 2025-05-26 | 2027-05-18 | 2025-05-26 | 2027-05-04
PCS_PJ02 | EN.C1.0050 | Completed | OMEGA.UD.[AUG23].EN.C1.CIV | RC Structural Drawings C1 | EN | CV | 100 | 100 | 0 | 0 | 0 | 7 | 2025-05-16 | 2027-05-09 | 2025-05-20 | 2027-05-04 | 2025-05-20 | 2027-05-11
PCS_PJ02 | CN.C3.0080 | In Progress | OMEGA.UD.[AUG23].CN.C3.MEC | Install Mechanical Components C3 | CN | MC | 20 | 100 | 9523135.2 | 1904627.04 | 9523135.2 | 30 | 2025-05-23 | 2027-05-15 | 2025-05-10 | 2027-05-11 | 2025-05-10 | 2027-05-16
PCS_PJ02 | EN.C3.0010 | Completed | OMEGA.UD.[AUG23].EN.C3.CIV | Boreholes C3 | EN | CV | 100 | 100 | 0 | 0 | 0 | 5 | 2025-05-23 | 2027-05-10 | 2025-05-09 | 2027-05-16 | 2025-05-09 | 2027-05-23
PCS_PJ02 | EN.C2.0080 | Completed | OMEGA.UD.[AUG23].EN.C2.MEP | MEP-M Drawings C2 | EN | MM | 100 | 100 | 0 | 0 | 0 | 5 | 2025-05-17 | 2027-05-13 | 2025-05-19 | 2027-05-23 | 2025-05-19 | 2027-05-21
PCS_PJ02 | EN.C3.0030 | Completed | OMEGA.UD.[AUG23].EN.C3.ELC | Electrical Equipment Arrangement C3 | EN | EL | 100 | 100 | 0 | 0 | 0 | 8 | 2025-05-21 | 2027-05-04 | 2025-05-25 | 2027-05-21 | 2025-05-25 | 2027-06-12
PCS_PJ02 | MS.C4.0060 | Not Started | OMEGA.UD.[AUG23].MS.ST | C4 Finish |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2025-06-13 | 2027-06-05 | 2025-06-16 | 2027-06-12 | 2025-06-16 | 2027-06-25
PCS_PJ02 | MS.C3.0050 | Not Started | OMEGA.UD.[AUG23].MS.ST | C3 Finish |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2025-06-04 | 2027-06-13 | 2025-06-07 | 2027-06-25 | 2025-06-07 | 2027-06-05
PCS_PJ02 | PC.GE.0070 | Completed | OMEGA.UD.[AUG23].PC | MEP-M | PC | MM | 100 | 100 | 400184.8 | 400184.8 | 400184.8 | 30 | 2025-06-27 | 2027-06-09 | 2025-06-14 | 2027-06-05 | 2025-06-14 | 2027-06-13
PCS_PJ02 | EN.C2.0060 | Completed | OMEGA.UD.[AUG23].EN.C2.CIV | Steel Drawings C2 | EN | CV | 100 | 100 | 0 | 0 | 0 | 12 | 2025-06-08 | 2027-06-14 | 2025-06-16 | 2027-06-13 | 2025-06-16 | 2027-06-16
PCS_PJ02 | CN.C2.0070 | Not Started | OMEGA.UD.[AUG23].CN.C2.CIV | Steel Sandwich Panels C2 | CN | CV | 0 | 68.42 | 816936 | 0 | 558956.21 | 19 | 2025-06-03 | 2027-06-18 | 2025-06-15 | 2027-06-16 | 2025-06-15 | 2027-06-06
PCS_PJ02 | CN.C3.0040 | Completed | OMEGA.UD.[AUG23].CN.C3.CIV | RC SubStructure C3 | CN | CV | 100 | 100 | 1900625.6 | 1900625.6 | 1900625.6 | 24 | 2025-06-21 | 2027-06-08 | 2025-06-26 | 2027-06-06 | 2025-06-26 | 2027-06-10
PCS_PJ02 | CN.C2.0010 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | Excavation C2 | CN | CV | 100 | 100 | 1067017.6 | 1067017.6 | 1067017.6 | 20 | 2025-06-15 | 2027-06-24 | 2025-06-27 | 2027-06-10 | 2025-06-27 | 2027-06-01
PCS_PJ02 | EN.C1.0040 | Completed | OMEGA.UD.[AUG23].EN.C1.CIV | Architectural Drawings C1 | EN | CV | 100 | 100 | 0 | 0 | 0 | 6 | 2025-06-02 | 2027-06-10 | 2025-06-01 | 2027-06-01 | 2025-06-01 | 2027-06-16
PCS_PJ02 | CN.C2.0050 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | RC SuperStructure C2 | CN | CV | 100 | 100 | 2090938.4 | 2090938.4 | 2090938.4 | 18 | 2025-06-01 | 2027-06-06 | 2025-06-19 | 2027-06-16 | 2025-06-19 | 2027-06-01
PCS_PJ02 | MS.C1.0030 | Not Started | OMEGA.UD.[AUG23].MS.ST | C1 Finish |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2025-06-04 | 2027-06-16 | 2025-06-04 | 2027-06-01 | 2025-06-04 | 2027-07-17
PCS_PJ02 | CN.C4.0010 | Completed | OMEGA.UD.[AUG23].CN.C4.CIV | Excavation C4 | CN | CV | 100 | 100 | 1067017.6 | 1067017.6 | 1067017.6 | 20 | 2025-07-14 | 2027-07-11 | 2025-07-19 | 2027-07-17 | 2025-07-19 | 2027-07-03
PCS_PJ02 | EN.C4.0070 | Completed | OMEGA.UD.[AUG23].EN.C4.MEP | MEP-E Drawings C4 | EN | ME | 100 | 100 | 0 | 0 | 0 | 5 | 2025-07-12 | 2027-07-09 | 2025-07-17 | 2027-07-03 | 2025-07-17 | 2027-07-07
PCS_PJ02 | EN.C4.0080 | Completed | OMEGA.UD.[AUG23].EN.C4.MEP | MEP-M Drawings C4 | EN | MM | 100 | 100 | 0 | 0 | 0 | 5 | 2025-07-03 | 2027-07-11 | 2025-07-10 | 2027-07-07 | 2025-07-10 | 2027-07-24
PCS_PJ02 | PC.GE.0060 | Completed | OMEGA.UD.[AUG23].PC | MEP-E | PC | ME | 100 | 100 | 594660 | 594660 | 594660 | 30 | 2025-07-14 | 2027-07-10 | 2025-07-04 | 2027-07-24 | 2025-07-04 | 2027-07-05
PCS_PJ02 | EN.C4.0060 | Completed | OMEGA.UD.[AUG23].EN.C4.CIV | Steel Drawings C4 | EN | CV | 100 | 100 | 0 | 0 | 0 | 12 | 2025-07-16 | 2027-07-01 | 2025-07-14 | 2027-07-05 | 2025-07-14 | 2027-07-04
PCS_PJ02 | CN.C4.0040 | Completed | OMEGA.UD.[AUG23].CN.C4.CIV | RC SubStructure C4 | CN | CV | 100 | 100 | 1900625.6 | 1900625.6 | 1900625.6 | 24 | 2025-07-09 | 2027-07-18 | 2025-07-21 | 2027-07-04 | 2025-07-21 | 2027-07-20
PCS_PJ02 | PC.GE.0040 | Completed | OMEGA.UD.[AUG23].PC | Electrical Equipment | PC | EL | 100 | 100 | 46900305.6 | 46900305.6 | 46900305.6 | 90 | 2025-07-10 | 2027-07-01 | 2025-07-13 | 2027-07-20 | 2025-07-13 | 2027-07-24
PCS_PJ02 | CN.C3.0110 | Not Started | OMEGA.UD.[AUG23].CN.C3.MEP | Install MEP-M C3 | CN | MM | 0 | 0 | 53871.2 | 0 | 0 | 10 | 2025-07-03 | 2027-07-20 | 2025-07-26 | 2027-07-24 | 2025-07-26 | 2027-07-26
PCS_PJ02 | CN.C1.0020 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | Backfilling C1 | CN | CV | 100 | 100 | 966984.8 | 966984.8 | 966984.8 | 10 | 2025-07-05 | 2027-07-23 | 2025-07-12 | 2027-07-26 | 2025-07-12 | 2027-08-12
PCS_PJ02 | EN.C2.0070 | Completed | OMEGA.UD.[AUG23].EN.C2.MEP | MEP-E Drawings C2 | EN | ME | 100 | 100 | 0 | 0 | 0 | 5 | 2025-08-12 | 2027-08-05 | 2025-08-19 | 2027-08-12 | 2025-08-19 | 2027-08-18
PCS_PJ02 | EN.GE.0020 | Completed | OMEGA.UD.[AUG23].EN.GE | SLD | EN | EL | 100 | 100 | 0 | 0 | 0 | 7 | 2025-08-07 | 2027-08-14 | 2025-08-09 | 2027-08-18 | 2025-08-09 | 2027-08-09
PCS_PJ02 | CN.C1.0120 | Not Started | OMEGA.UD.[AUG23].CN.C1.C&P | Install Control System C1 | CN | CP | 0 | 7.14 | 1624488 | 0 | 116034.86 | 28 | 2025-08-28 | 2027-08-28 | 2025-08-08 | 2027-08-09 | 2025-08-08 | 2027-08-13
PCS_PJ02 | PC.GE.0090 | Completed | OMEGA.UD.[AUG23].PC | Control Cables | PC | CP | 100 | 100 | 3323894.4 | 3323894.4 | 3323894.4 | 90 | 2025-08-04 | 2027-08-13 | 2025-08-07 | 2027-08-13 | 2025-08-07 | 2027-08-03
PCS_PJ02 | PC.GE.0050 | Completed | OMEGA.UD.[AUG23].PC | Electrical Cables | PC | EL | 100 | 100 | 5499250.4 | 5499250.4 | 5499250.4 | 60 | 2025-08-15 | 2027-08-13 | 2025-08-25 | 2027-08-03 | 2025-08-25 | 2027-08-10
PCS_PJ02 | CN.C3.0020 | Completed | OMEGA.UD.[AUG23].CN.C3.CIV | Backfilling C3 | CN | CV | 100 | 100 | 966984.8 | 966984.8 | 966984.8 | 10 | 2025-08-22 | 2027-08-18 | 2025-08-09 | 2027-08-10 | 2025-08-09 | 2027-08-05
PCS_PJ02 | TS.C3.0050 | Not Started | OMEGA.UD.[AUG23].TS.C3.C&P | Control Testing C3 | TS | CP | 0 | 0 | 0 | 0 | 0 | 6 | 2025-08-14 | 2027-08-07 | 2025-08-09 | 2027-08-05 | 2025-08-09 | 2027-08-23
PCS_PJ02 | EN.C1.0080 | Completed | OMEGA.UD.[AUG23].EN.C1.MEP | MEP-M Drawings C1 | EN | MM | 100 | 100 | 0 | 0 | 0 | 5 | 2025-08-14 | 2027-08-09 | 2025-08-02 | 2027-08-23 | 2025-08-02 | 2027-08-16
PCS_PJ02 | PC.GE.0030 | Completed | OMEGA.UD.[AUG23].PC | Mechanical Components | PC | MC | 100 | 100 | 70743292 | 70743292 | 70743292 | 90 | 2025-08-11 | 2027-08-21 | 2025-08-13 | 2027-08-16 | 2025-08-13 | 2027-08-20
PCS_PJ02 | EN.C3.0050 | Completed | OMEGA.UD.[AUG23].EN.C3.CIV | RC Structural Drawings C3 | EN | CV | 100 | 100 | 0 | 0 | 0 | 7 | 2025-08-01 | 2027-08-02 | 2025-08-16 | 2027-08-20 | 2025-08-16 | 2027-09-12
PCS_PJ02 | EN.C3.0080 | Completed | OMEGA.UD.[AUG23].EN.C3.MEP | MEP-M Drawings C3 | EN | MM | 100 | 100 | 0 | 0 | 0 | 5 | 2025-09-08 | 2027-09-23 | 2025-09-08 | 2027-09-12 | 2025-09-08 | 2027-09-17
PCS_PJ02 | CN.C3.0090 | Not Started | OMEGA.UD.[AUG23].CN.C3.ELC | Install Electrical Equipment C3 | CN | EL | 0 | 0 | 7053786.4 | 0 | 0 | 22 | 2025-09-25 | 2027-09-17 | 2025-09-20 | 2027-09-17 | 2025-09-20 | 2027-09-06
PCS_PJ02 | CN.C1.0090 | Not Started | OMEGA.UD.[AUG23].CN.C1.ELC | Install Electrical Equipment C1 | CN | EL | 0 | 100 | 7053786.4 | 0 | 7053786.4 | 22 | 2025-09-24 | 2027-09-16 | 2025-09-06 | 2027-09-06 | 2025-09-06 | 2027-09-15
PCS_PJ02 | EN.C4.0030 | Completed | OMEGA.UD.[AUG23].EN.C4.ELC | Electrical Equipment Arrangement C4 | EN | EL | 100 | 100 | 0 | 0 | 0 | 8 | 2025-09-25 | 2027-09-01 | 2025-09-15 | 2027-09-15 | 2025-09-15 | 2027-09-24
PCS_PJ02 | EN.C1.0060 | Completed | OMEGA.UD.[AUG23].EN.C1.CIV | Steel Drawings C1 | EN | CV | 100 | 100 | 0 | 0 | 0 | 12 | 2025-09-05 | 2027-09-20 | 2025-09-18 | 2027-09-24 | 2025-09-18 | 2027-09-10
PCS_PJ02 | EN.C2.0050 | Completed | OMEGA.UD.[AUG23].EN.C2.CIV | RC Structural Drawings C2 | EN | CV | 100 | 100 | 0 | 0 | 0 | 7 | 2025-09-09 | 2027-09-23 | 2025-09-22 | 2027-09-10 | 2025-09-22 | 2027-09-10
PCS_PJ02 | CN.C2.0100 | Not Started | OMEGA.UD.[AUG23].CN.C2.MEP | Install MEP-E C2 | CN | ME | 0 | 33.33 | 80050.4 | 0 | 26683.47 | 9 | 2025-09-21 | 2027-09-12 | 2025-09-14 | 2027-09-10 | 2025-09-14 | 2027-09-23
PCS_PJ02 | TS.C2.0030 | Not Started | OMEGA.UD.[AUG23].TS.C2.MEP | MEP-E Testing C2 | TS | ME | 0 | 0 | 0 | 0 | 0 | 6 | 2025-09-21 | 2027-09-20 | 2025-09-14 | 2027-09-23 | 2025-09-14 | 2027-09-05
PCS_PJ02 | CN.C4.0020 | Completed | OMEGA.UD.[AUG23].CN.C4.CIV | Backfilling C4 | CN | CV | 100 | 100 | 966984.8 | 966984.8 | 966984.8 | 10 | 2025-09-09 | 2027-09-11 | 2025-09-11 | 2027-09-05 | 2025-09-11 | 2027-09-20
PCS_PJ02 | CN.C1.0040 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | RC SubStructure C1 | CN | CV | 100 | 100 | 1900625.6 | 1900625.6 | 1900625.6 | 24 | 2025-09-03 | 2027-09-18 | 2025-09-15 | 2027-09-20 | 2025-09-15 | 2027-10-14
PCS_PJ02 | CN.C3.0010 | Completed | OMEGA.UD.[AUG23].CN.C3.CIV | Excavation C3 | CN | CV | 100 | 100 | 1067017.6 | 1067017.6 | 1067017.6 | 20 | 2025-10-13 | 2027-10-27 | 2025-10-13 | 2027-10-14 | 2025-10-13 | 2027-10-04
PCS_PJ02 | CN.C2.0120 | Not Started | OMEGA.UD.[AUG23].CN.C2.C&P | Install Control System C2 | CN | CP | 0 | 0 | 1624488 | 0 | 0 | 28 | 2025-10-04 | 2027-10-10 | 2025-10-10 | 2027-10-04 | 2025-10-10 | 2027-10-22
PCS_PJ02 | TS.C4.0020 | Not Started | OMEGA.UD.[AUG23].TS.C4.ELC | Electrical Testing C4 | TS | EL | 0 | 0 | 0 | 0 | 0 | 6 | 2025-10-26 | 2027-10-14 | 2025-10-28 | 2027-10-22 | 2025-10-28 | 2027-10-14
PCS_PJ02 | CN.C2.0080 | Completed | OMEGA.UD.[AUG23].CN.C2.MEC | Install Mechanical Components C2 | CN | MC | 100 | 100 | 9523135.2 | 9523135.2 | 9523135.2 | 30 | 2025-10-18 | 2027-10-11 | 2025-10-01 | 2027-10-14 | 2025-10-01 | 2027-10-17
PCS_PJ02 | CN.C2.0110 | Not Started | OMEGA.UD.[AUG23].CN.C2.MEP | Install MEP-M C2 | CN | MM | 0 | 0 | 53871.2 | 0 | 0 | 10 | 2025-10-24 | 2027-10-23 | 2025-10-07 | 2027-10-17 | 2025-10-07 | 2027-10-11
PCS_PJ02 | CN.C1.0030 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | PC C1 | CN | CV | 100 | 100 | 160052.8 | 160052.8 | 160052.8 | 16 | 2025-10-13 | 2027-10-11 | 2025-10-13 | 2027-10-11 | 2025-10-13 | 2027-10-09
PCS_PJ02 | TS.C1.0020 | Not Started | OMEGA.UD.[AUG23].TS.C1.ELC | Electrical Testing C1 | TS | EL | 0 | 33.33 | 0 | 0 | 0 | 6 | 2025-10-07 | 2027-10-23 | 2025-10-01 | 2027-10-09 | 2025-10-01 | 2027-10-27
PCS_PJ02 | CN.C4.0110 | Not Started | OMEGA.UD.[AUG23].CN.C4.MEP | Install MEP-M C4 | CN | MM | 0 | 0 | 53871.2 | 0 | 0 | 10 | 2025-10-23 | 2027-10-02 | 2025-10-23 | 2027-10-27 | 2025-10-23 | 2027-10-19
PCS_PJ02 | EN.C1.0070 | Completed | OMEGA.UD.[AUG23].EN.C1.MEP | MEP-E Drawings C1 | EN | ME | 100 | 100 | 0 | 0 | 0 | 5 | 2025-10-09 | 2027-10-26 | 2025-10-15 | 2027-10-19 | 2025-10-15 | 2027-10-07
PCS_PJ02 | TS.C2.0020 | Not Started | OMEGA.UD.[AUG23].TS.C2.ELC | Electrical Testing C2 | TS | EL | 0 | 0 | 0 | 0 | 0 | 6 | 2025-10-05 | 2027-10-13 | 2025-10-01 | 2027-10-07 | 2025-10-01 | 2027-11-19
PCS_PJ02 | TS.C1.0040 | Not Started | OMEGA.UD.[AUG23].TS.C1.MEP | MEP-M Testing C1 | TS | MM | 0 | 100 | 0 | 0 | 0 | 6 | 2025-11-26 | 2027-11-04 | 2025-11-07 | 2027-11-19 | 2025-11-07 | 2027-11-11
PCS_PJ02 | EN.C3.0060 | Completed | OMEGA.UD.[AUG23].EN.C3.CIV | Steel Drawings C3 | EN | CV | 100 | 100 | 0 | 0 | 0 | 12 | 2025-11-09 | 2027-11-21 | 2025-11-22 | 2027-11-11 | 2025-11-22 | 2027-11-09
PCS_PJ02 | TS.C1.0050 | Not Started | OMEGA.UD.[AUG23].TS.C1.C&P | Control Testing C1 | TS | CP | 0 | 0 | 0 | 0 | 0 | 6 | 2025-11-05 | 2027-11-09 | 2025-11-25 | 2027-11-09 | 2025-11-25 | 2027-11-19
PCS_PJ02 | EN.C4.0050 | Completed | OMEGA.UD.[AUG23].EN.C4.CIV | RC Structural Drawings C4 | EN | CV | 100 | 100 | 0 | 0 | 0 | 7 | 2025-11-22 | 2027-11-10 | 2025-11-24 | 2027-11-19 | 2025-11-24 | 2027-11-28
PCS_PJ02 | CN.C3.0120 | Not Started | OMEGA.UD.[AUG23].CN.C3.C&P | Install Control System C3 | CN | CP | 0 | 0 | 1624488 | 0 | 0 | 28 | 2025-11-11 | 2027-11-02 | 2025-11-13 | 2027-11-28 | 2025-11-13 | 2027-11-27
PCS_PJ02 | CN.C2.0030 | Completed | OMEGA.UD.[AUG23].CN.C2.CIV | PC C2 | CN | CV | 100 | 100 | 160052.8 | 160052.8 | 160052.8 | 16 | 2025-11-20 | 2027-11-28 | 2025-11-26 | 2027-11-27 | 2025-11-26 | 2027-11-07
PCS_PJ02 | CN.C4.0080 | Not Started | OMEGA.UD.[AUG23].CN.C4.MEC | Install Mechanical Components C4 | CN | MC | 0 | 16.67 | 9523135.2 | 0 | 1587189.2 | 30 | 2025-11-22 | 2027-11-02 | 2025-11-21 | 2027-11-07 | 2025-11-21 | 2027-11-14
PCS_PJ02 | CN.C4.0120 | Not Started | OMEGA.UD.[AUG23].CN.C4.C&P | Install Control System C4 | CN | CP | 0 | 0 | 1624488 | 0 | 0 | 28 | 2025-11-26 | 2027-11-15 | 2025-11-28 | 2027-11-14 | 2025-11-28 | 2027-11-05
PCS_PJ02 | EN.C3.0070 | Completed | OMEGA.UD.[AUG23].EN.C3.MEP | MEP-E Drawings C3 | EN | ME | 100 | 100 | 0 | 0 | 0 | 5 | 2025-11-26 | 2027-11-16 | 2025-11-18 | 2027-11-05 | 2025-11-18 | 2027-11-13
PCS_PJ02 | CN.C1.0010 | Completed | OMEGA.UD.[AUG23].CN.C1.CIV | Excavation C1 | CN | CV | 100 | 100 | 1067017.6 | 1067017.6 | 1067017.6 | 20 | 2025-11-14 | 2027-11-06 | 2025-11-20 | 2027-11-13 | 2025-11-20 | 2027-12-22
PCS_PJ02 | CN.C4.0030 | Completed | OMEGA.UD.[AUG23].CN.C4.CIV | PC C4 | CN | CV | 100 | 100 | 160052.8 | 160052.8 | 160052.8 | 16 | 2025-12-26 | 2027-12-10 | 2025-12-10 | 2027-12-22 | 2025-12-10 | 2027-12-17
PCS_PJ02 | MS.GE.0010 | Completed | OMEGA.UD.[AUG23].MS.OA | Project Start |  |  | 100 | 100 | 0 | 0 | 0 | 0 | 2025-12-09 | 2027-12-14 | 2025-12-16 | 2027-12-17 | 2025-12-16 | 2027-12-19
PCS_PJ02 | EN.C2.0010 | Completed | OMEGA.UD.[AUG23].EN.C2.CIV | Boreholes C2 | EN | CV | 100 | 100 | 0 | 0 | 0 | 5 | 2025-12-21 | 2027-12-11 | 2025-12-12 | 2027-12-19 | 2025-12-12 | 2027-12-26
PCS_PJ02 | MS.GE.0020 | Not Started | OMEGA.UD.[AUG23].MS.OA | Project Finish |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2025-12-25 | 2027-12-08 | 2025-12-26 | 2027-12-26 | 2025-12-26 | 2027-12-21
PCS_PJ02 | EN.C1.0020 | Completed | OMEGA.UD.[AUG23].EN.C1.MEC | Mechanical General Arrangement C1 | EN | MC | 100 | 100 | 0 | 0 | 0 | 7 | 2025-12-04 | 2027-12-23 | 2025-12-20 | 2027-12-21 | 2025-12-20 | 2027-12-18
PCS_PJ02 | EN.C1.0010 | Completed | OMEGA.UD.[AUG23].EN.C1.CIV | Boreholes C1 | EN | CV | 100 | 100 | 0 | 0 | 0 | 5 | 2025-12-08 | 2027-12-24 | 2025-12-08 | 2027-12-18 | 2025-12-08 | 2027-12-12
PCS_PJ02 | PC.GE.0080 | Completed | OMEGA.UD.[AUG23].PC | Control System | PC | CP | 100 | 100 | 8743732 | 8743732 | 8743732 | 120 | 2025-12-07 | 2027-12-13 | 2025-12-17 | 2027-12-12 | 2025-12-17 | 2027-12-08
PCS_PJ02 | TS.C1.0010 | Not Started | OMEGA.UD.[AUG23].TS.C1.MEC | Mechanical Testing C1 | TS | MC | 0 | 100 | 0 | 0 | 0 | 6 | 2025-12-25 | 2027-12-17 | 2025-12-25 | 2027-12-08 | 2025-12-25 | 2027-12-23
PCS_PJ02 | TS.C1.0030 | Not Started | OMEGA.UD.[AUG23].TS.C1.MEP | MEP-E Testing C1 | TS | ME | 0 | 100 | 0 | 0 | 0 | 6 | 2025-12-09 | 2027-12-15 | 2025-12-01 | 2027-12-23 | 2025-12-01 | 2027-12-02
PCS_PJ02 | EN.C2.0030 | Completed | OMEGA.UD.[AUG23].EN.C2.ELC | Electrical Equipment Arrangement C2 | EN | EL | 100 | 100 | 0 | 0 | 0 | 8 | 2025-12-07 | 2027-12-04 | 2025-12-09 | 2027-12-02 | 2025-12-09 | 2028-01-27
PCS_PJ02 | EN.C3.0040 | Completed | OMEGA.UD.[AUG23].EN.C3.CIV | Architectural Drawings C3 | EN | CV | 100 | 100 | 0 | 0 | 0 | 6 | 2026-01-18 | 2028-01-11 | 2026-01-20 | 2028-01-27 | 2026-01-20 | 2028-01-25
PCS_PJ02 | CN.C4.0100 | Not Started | OMEGA.UD.[AUG23].CN.C4.MEP | Install MEP-E C4 | CN | ME | 0 | 0 | 80050.4 | 0 | 0 | 9 | 2026-01-07 | 2028-01-10 | 2026-01-21 | 2028-01-25 | 2026-01-21 | 0
Formulas:
Planned Start = DATE(2025,ROUNDUP(ROW([Project ID, row below])*12/118,0),RANDBETWEEN(1,28))
Planned Finish = DATE(2027,ROUNDUP(ROW([Project ID, row below])*12/118,0),RANDBETWEEN(1,28))
Actual Start = DATE(2025,ROUNDUP(ROW([Project ID, row below])*12/118,0),RANDBETWEEN(1,28))
Actual Finish = DATE(2027,ROUNDUP(ROW([Project ID, row below])*12/118,0),RANDBETWEEN(1,28))
Start = Activity_OMEGA_AUG23[[#This Row],[Actual Start]]
Finish = [Actual Finish, row below]

## RES. Baseline
Project ID | Activity ID | Code [Life Cycle] | Code [Trade] | Resource ID | Spreadsheet Field | time axis 2023-01-01 to 2023-12-31
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Budgeted Units | 2023-05-28: 13720962.13; 2023-06-04: 6860481.07
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Actual Units
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Remaining Units | 2023-05-28: 13720962.13; 2023-06-04: 6860481.07
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Budgeted Units | 2023-07-16: 6068664.8
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Actual Units
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Remaining Units | 2023-07-16: 6068664.8
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Budgeted Units | 2023-05-07: 55022560.44; 2023-05-14: 15720731.56
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Actual Units
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Remaining Units | 2023-05-07: 55022560.44; 2023-05-14: 15720731.56
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Budgeted Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Actual Units
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Remaining Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Budgeted Units | 2023-06-18: 3666166.93; 2023-07-02: 1833083.47
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Actual Units
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Remaining Units | 2023-06-18: 3666166.93; 2023-07-02: 1833083.47
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Budgeted Units | 2023-07-23: 594660
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Actual Units
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Remaining Units | 2023-07-23: 594660
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Budgeted Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Actual Units
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Remaining Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Budgeted Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Actual Units
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Remaining Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Budgeted Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Actual Units
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Remaining Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Budgeted Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Remaining Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Budgeted Units | 2023-04-09: 193396.96; 2023-04-23: 96698.48; 2023-04-30: 676889.36
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Remaining Units | 2023-04-09: 193396.96; 2023-04-23: 96698.48; 2023-04-30: 676889.36
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Remaining Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Budgeted Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Remaining Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 116163.24; 2023-03-26: 813142.71; 2023-04-02: 813142.71; 2023-04-09: 348489.73
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Remaining Units | 2023-03-19: 116163.24; 2023-03-26: 813142.71; 2023-04-02: 813142.71; 2023-04-09: 348489.73
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Budgeted Units | 2023-06-11: 503741.67; 2023-06-18: 755612.51; 2023-07-02: 125935.42; 2023-07-09: 881547.93; 2023-07-16: 503741.67
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Remaining Units | 2023-06-11: 503741.67; 2023-06-18: 755612.51; 2023-07-02: 125935.42; 2023-07-09: 881547.93; 2023-07-16: 503741.67
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 128989.89; 2023-07-23: 300976.42; 2023-07-30: 300976.42; 2023-08-06: 85993.26
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Remaining Units | 2023-07-16: 128989.89; 2023-07-23: 300976.42; 2023-07-30: 300976.42; 2023-08-06: 85993.26
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Budgeted Units | 2023-05-14: 1904627.04; 2023-05-21: 2222064.88; 2023-05-28: 2222064.88; 2023-06-04: 2222064.88; 2023-06-11: 952313.52
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Actual Units
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Remaining Units | 2023-05-14: 1904627.04; 2023-05-21: 2222064.88; 2023-05-28: 2222064.88; 2023-06-04: 2222064.88; 2023-06-11: 952313.52
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Budgeted Units | 2023-08-06: 1603133.27; 2023-08-13: 2244386.58; 2023-08-20: 2244386.58; 2023-08-27: 961879.96
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Remaining Units | 2023-08-06: 1603133.27; 2023-08-13: 2244386.58; 2023-08-20: 2244386.58; 2023-08-27: 961879.96
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Budgeted Units | 2023-07-30: 62261.42; 2023-08-06: 17788.98
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Remaining Units | 2023-07-30: 62261.42; 2023-08-06: 17788.98
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Budgeted Units | 2023-08-06: 26935.6; 2023-08-13: 26935.6
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Remaining Units | 2023-08-06: 26935.6; 2023-08-13: 26935.6
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Budgeted Units | 2023-08-27: 232069.71; 2023-09-03: 406122; 2023-09-10: 406122; 2023-09-17: 406122; 2023-09-24: 174052.29
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Remaining Units | 2023-08-27: 232069.71; 2023-09-03: 406122; 2023-09-10: 406122; 2023-09-17: 406122; 2023-09-24: 174052.29
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Remaining Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Budgeted Units | 2023-05-21: 676889.36; 2023-05-28: 290095.44
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Remaining Units | 2023-05-21: 676889.36; 2023-05-28: 290095.44
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Remaining Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 79192.73; 2023-03-26: 554349.13; 2023-04-02: 554349.13; 2023-04-09: 395963.67; 2023-04-23: 79192.73; 2023-04-30: 237578.2
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Remaining Units | 2023-03-19: 79192.73; 2023-03-26: 554349.13; 2023-04-02: 554349.13; 2023-04-09: 395963.67; 2023-04-23: 79192.73; 2023-04-30: 237578.2
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 464652.98; 2023-05-07: 813142.71; 2023-05-14: 813142.71
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Remaining Units | 2023-04-30: 464652.98; 2023-05-07: 813142.71; 2023-05-14: 813142.71
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Budgeted Units | 2023-07-23: 251870.84; 2023-07-30: 881547.93; 2023-08-06: 881547.93; 2023-08-13: 755612.51
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Remaining Units | 2023-07-23: 251870.84; 2023-07-30: 881547.93; 2023-08-06: 881547.93; 2023-08-13: 755612.51
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Budgeted Units | 2023-08-13: 42996.63; 2023-08-20: 300976.42; 2023-08-27: 300976.42; 2023-09-03: 171986.53
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Remaining Units | 2023-08-13: 42996.63; 2023-08-20: 300976.42; 2023-08-27: 300976.42; 2023-09-03: 171986.53
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Budgeted Units | 2023-06-11: 1269751.36; 2023-06-18: 1904627.04; 2023-07-02: 317437.84; 2023-07-09: 2222064.88; 2023-07-16: 2222064.88; 2023-07-23: 1587189.2
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Actual Units
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Remaining Units | 2023-06-11: 1269751.36; 2023-06-18: 1904627.04; 2023-07-02: 317437.84; 2023-07-09: 2222064.88; 2023-07-16: 2222064.88; 2023-07-23: 1587189.2
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Budgeted Units | 2023-09-03: 961879.96; 2023-09-10: 2244386.58; 2023-09-17: 2244386.58; 2023-09-24: 1603133.27
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Remaining Units | 2023-09-03: 961879.96; 2023-09-10: 2244386.58; 2023-09-17: 2244386.58; 2023-09-24: 1603133.27
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Budgeted Units | 2023-08-27: 44472.44; 2023-09-03: 35577.96
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Remaining Units | 2023-08-27: 44472.44; 2023-09-03: 35577.96
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Budgeted Units | 2023-09-03: 16161.36; 2023-09-10: 37709.84
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Remaining Units | 2023-09-03: 16161.36; 2023-09-10: 37709.84
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Budgeted Units | 2023-09-24: 116034.86; 2023-10-01: 406122; 2023-10-08: 406122; 2023-10-15: 406122; 2023-10-22: 290087.14
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Remaining Units | 2023-09-24: 116034.86; 2023-10-01: 406122; 2023-10-08: 406122; 2023-10-15: 406122; 2023-10-22: 290087.14
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Remaining Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Budgeted Units | 2023-06-11: 386793.92; 2023-06-18: 580190.88
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Remaining Units | 2023-06-11: 386793.92; 2023-06-18: 580190.88
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Remaining Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 316770.93; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 475156.4
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Remaining Units | 2023-04-30: 316770.93; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 475156.4
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Budgeted Units | 2023-05-21: 116163.24; 2023-05-28: 813142.71; 2023-06-04: 813142.71; 2023-06-11: 348489.73
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Remaining Units | 2023-05-21: 116163.24; 2023-05-28: 813142.71; 2023-06-04: 813142.71; 2023-06-11: 348489.73
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Budgeted Units | 2023-08-27: 881547.93; 2023-09-03: 881547.93; 2023-09-10: 881547.93; 2023-09-17: 125935.42
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Remaining Units | 2023-08-27: 881547.93; 2023-09-03: 881547.93; 2023-09-10: 881547.93; 2023-09-17: 125935.42
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Budgeted Units | 2023-09-17: 257979.79; 2023-09-24: 300976.42; 2023-10-01: 257979.79
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Remaining Units | 2023-09-17: 257979.79; 2023-09-24: 300976.42; 2023-10-01: 257979.79
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Budgeted Units | 2023-07-23: 634875.68; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 2222064.88; 2023-08-20: 2222064.88
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Actual Units
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Remaining Units | 2023-07-23: 634875.68; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 2222064.88; 2023-08-20: 2222064.88
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Budgeted Units | 2023-10-01: 320626.65; 2023-10-08: 2244386.58; 2023-10-15: 2244386.58; 2023-10-22: 2244386.58
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Remaining Units | 2023-10-01: 320626.65; 2023-10-08: 2244386.58; 2023-10-15: 2244386.58; 2023-10-22: 2244386.58
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Budgeted Units | 2023-09-24: 26683.47; 2023-10-01: 53366.93
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Remaining Units | 2023-09-24: 26683.47; 2023-10-01: 53366.93
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Budgeted Units | 2023-10-01: 5387.12; 2023-10-08: 37709.84; 2023-10-15: 10774.24
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Remaining Units | 2023-10-01: 5387.12; 2023-10-08: 37709.84; 2023-10-15: 10774.24
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Budgeted Units | 2023-10-29: 406122; 2023-11-05: 406122; 2023-11-12: 406122; 2023-11-19: 406122
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Remaining Units | 2023-10-29: 406122; 2023-11-05: 406122; 2023-11-12: 406122; 2023-11-19: 406122
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Remaining Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 96698.48; 2023-07-23: 676889.36; 2023-07-30: 193396.96
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Remaining Units | 2023-07-16: 96698.48; 2023-07-23: 676889.36; 2023-07-30: 193396.96
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Budgeted Units | 2023-04-23: 10003.3; 2023-04-30: 70023.1; 2023-05-07: 70023.1; 2023-05-14: 10003.3
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Remaining Units | 2023-04-23: 10003.3; 2023-04-30: 70023.1; 2023-05-07: 70023.1; 2023-05-14: 10003.3
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Budgeted Units | 2023-05-21: 79192.73; 2023-05-28: 554349.13; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 158385.47
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Remaining Units | 2023-05-21: 79192.73; 2023-05-28: 554349.13; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 158385.47
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Budgeted Units | 2023-06-18: 464652.98; 2023-07-02: 116163.24; 2023-07-09: 813142.71; 2023-07-16: 696979.47
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Remaining Units | 2023-06-18: 464652.98; 2023-07-02: 116163.24; 2023-07-09: 813142.71; 2023-07-16: 696979.47
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Budgeted Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Remaining Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Budgeted Units | 2023-10-15: 171986.53; 2023-10-22: 300976.42; 2023-10-29: 300976.42; 2023-11-05: 42996.63
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Remaining Units | 2023-10-15: 171986.53; 2023-10-22: 300976.42; 2023-10-29: 300976.42; 2023-11-05: 42996.63
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Budgeted Units | 2023-08-27: 2222064.88; 2023-09-03: 2222064.88; 2023-09-10: 2222064.88; 2023-09-17: 2222064.88; 2023-09-24: 634875.68
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Actual Units
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Remaining Units | 2023-08-27: 2222064.88; 2023-09-03: 2222064.88; 2023-09-10: 2222064.88; 2023-09-17: 2222064.88; 2023-09-24: 634875.68
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Budgeted Units | 2023-11-05: 1923759.93; 2023-11-12: 2244386.58; 2023-11-19: 2244386.58; 2023-11-26: 641253.31
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Remaining Units | 2023-11-05: 1923759.93; 2023-11-12: 2244386.58; 2023-11-19: 2244386.58; 2023-11-26: 641253.31
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Budgeted Units | 2023-10-22: 8894.49; 2023-10-29: 62261.42; 2023-11-05: 8894.49
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Remaining Units | 2023-10-22: 8894.49; 2023-10-29: 62261.42; 2023-11-05: 8894.49
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Budgeted Units | 2023-11-05: 32322.72; 2023-11-12: 21548.48
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Remaining Units | 2023-11-05: 32322.72; 2023-11-12: 21548.48
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Budgeted Units | 2023-11-26: 290087.14; 2023-12-03: 406122; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 116034.86
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Remaining Units | 2023-11-26: 290087.14; 2023-12-03: 406122; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 116034.86
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Budgeted Units | 2023-01-01: 786540.83
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Actual Units
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Remaining Units | 2023-01-01: 786540.83
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Budgeted Units | 2023-01-01: 674177.85; 2023-01-08: 112362.98
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Actual Units
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Remaining Units | 2023-01-01: 674177.85; 2023-01-08: 112362.98
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Budgeted Units | 2023-01-08: 471924.5; 2023-01-15: 314616.33
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Actual Units
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Remaining Units | 2023-01-08: 471924.5; 2023-01-15: 314616.33
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 786540.83
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Remaining Units | 2023-01-01: 786540.83
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-01: 674177.85; 2023-01-08: 112362.98
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Actual Units
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Remaining Units | 2023-01-01: 674177.85; 2023-01-08: 112362.98
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-08: 589905.62; 2023-01-15: 196635.21
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Actual Units
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Remaining Units | 2023-01-08: 589905.62; 2023-01-15: 196635.21
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 131090.14; 2023-01-08: 655450.69
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Remaining Units | 2023-01-01: 131090.14; 2023-01-08: 655450.69
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 561814.88; 2023-01-22: 224725.95
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Remaining Units | 2023-01-15: 561814.88; 2023-01-22: 224725.95
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 327725.35; 2023-01-29: 458815.48
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Remaining Units | 2023-01-22: 327725.35; 2023-01-29: 458815.48
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-08: 314616.33; 2023-01-15: 471924.5
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Actual Units
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Remaining Units | 2023-01-08: 314616.33; 2023-01-15: 471924.5
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-08: 314616.33; 2023-01-15: 471924.5
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Actual Units
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Remaining Units | 2023-01-08: 314616.33; 2023-01-15: 471924.5
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 157308.17; 2023-01-08: 629232.66
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Remaining Units | 2023-01-01: 157308.17; 2023-01-08: 629232.66
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-08: 674177.85; 2023-01-15: 112362.98
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Actual Units
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Remaining Units | 2023-01-08: 674177.85; 2023-01-15: 112362.98
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-15: 491588.02; 2023-01-22: 294952.81
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Actual Units
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Remaining Units | 2023-01-15: 491588.02; 2023-01-22: 294952.81
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 262180.28; 2023-01-15: 524360.55
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Remaining Units | 2023-01-08: 262180.28; 2023-01-15: 524360.55
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 449451.9; 2023-01-29: 337088.93
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Remaining Units | 2023-01-22: 449451.9; 2023-01-29: 337088.93
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 262180.28; 2023-02-05: 458815.48; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Remaining Units | 2023-01-29: 262180.28; 2023-02-05: 458815.48; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-15: 471924.5; 2023-01-22: 314616.33
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Actual Units
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Remaining Units | 2023-01-15: 471924.5; 2023-01-22: 314616.33
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-15: 471924.5; 2023-01-22: 314616.33
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Actual Units
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Remaining Units | 2023-01-15: 471924.5; 2023-01-22: 314616.33
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 471924.5; 2023-01-15: 314616.33
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Remaining Units | 2023-01-08: 471924.5; 2023-01-15: 314616.33
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-15: 674177.85; 2023-01-22: 112362.98
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Actual Units
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Remaining Units | 2023-01-15: 674177.85; 2023-01-22: 112362.98
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-22: 393270.42; 2023-01-29: 393270.42
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Actual Units
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Remaining Units | 2023-01-22: 393270.42; 2023-01-29: 393270.42
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 393270.42; 2023-01-22: 393270.42
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Remaining Units | 2023-01-15: 393270.42; 2023-01-22: 393270.42
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 337088.93; 2023-02-05: 449451.9
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Remaining Units | 2023-01-29: 337088.93; 2023-02-05: 449451.9
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 196635.21; 2023-02-12: 458815.48; 2023-02-19: 131090.14
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Remaining Units | 2023-02-05: 196635.21; 2023-02-12: 458815.48; 2023-02-19: 131090.14
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-22: 629232.66; 2023-01-29: 157308.17
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Actual Units
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Remaining Units | 2023-01-22: 629232.66; 2023-01-29: 157308.17
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-22: 629232.66; 2023-01-29: 157308.17
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Actual Units
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Remaining Units | 2023-01-22: 629232.66; 2023-01-29: 157308.17
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 786540.83
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Remaining Units | 2023-01-15: 786540.83
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-22: 674177.85; 2023-01-29: 112362.98
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Actual Units
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Remaining Units | 2023-01-22: 674177.85; 2023-01-29: 112362.98
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-29: 294952.81; 2023-02-05: 491588.02
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Actual Units
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Remaining Units | 2023-01-29: 294952.81; 2023-02-05: 491588.02
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 524360.55; 2023-01-29: 262180.28
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Remaining Units | 2023-01-22: 524360.55; 2023-01-29: 262180.28
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 224725.95; 2023-02-12: 561814.88
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Remaining Units | 2023-02-05: 224725.95; 2023-02-12: 561814.88
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-12: 131090.14; 2023-02-19: 458815.48; 2023-02-26: 196635.21
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Actual Units
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Remaining Units | 2023-02-12: 131090.14; 2023-02-19: 458815.48; 2023-02-26: 196635.21
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-29: 786540.83
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Actual Units
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Remaining Units | 2023-01-29: 786540.83
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-29: 786540.83
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Actual Units
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Remaining Units | 2023-01-29: 786540.83
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Budgeted Units | 2023-03-19: 1166281.77; 2023-03-26: 2040993.09; 2023-04-02: 2040993.09; 2023-04-09: 1457852.21; 2023-04-23: 291570.44; 2023-04-30: 2040993.09; 2023-05-07: 2040993.09; 2023-05-14: 2040993.09; 2023-05-21: 2040993.09; 2023-05-28: 2040993.09; 2023-06-04: 291570.44
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Actual Units
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Remaining Units | 2023-03-19: 1166281.77; 2023-03-26: 2040993.09; 2023-04-02: 2040993.09; 2023-04-09: 1457852.21; 2023-04-23: 291570.44; 2023-04-30: 2040993.09; 2023-05-07: 2040993.09; 2023-05-14: 2040993.09; 2023-05-21: 2040993.09; 2023-05-28: 2040993.09; 2023-06-04: 291570.44
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Budgeted Units | 2023-04-30: 85972.75; 2023-05-07: 601809.25; 2023-05-14: 601809.25; 2023-05-21: 601809.25; 2023-05-28: 601809.25; 2023-06-04: 601809.25; 2023-06-11: 601809.25; 2023-06-18: 515836.5; 2023-07-02: 85972.75; 2023-07-09: 601809.25; 2023-07-16: 257918.25
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Actual Units
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Remaining Units | 2023-04-30: 85972.75; 2023-05-07: 601809.25; 2023-05-14: 601809.25; 2023-05-21: 601809.25; 2023-05-28: 601809.25; 2023-06-04: 601809.25; 2023-06-11: 601809.25; 2023-06-18: 515836.5; 2023-07-02: 85972.75; 2023-07-09: 601809.25; 2023-07-16: 257918.25
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Budgeted Units | 2023-01-29: 4008786.52; 2023-02-05: 4676917.61; 2023-02-12: 4676917.61; 2023-02-19: 4676917.61; 2023-02-26: 4676917.61; 2023-03-05: 4676917.61; 2023-03-12: 4676917.61; 2023-03-19: 4676917.61; 2023-03-26: 4676917.61; 2023-04-02: 4676917.61; 2023-04-09: 3340655.44; 2023-04-23: 668131.09; 2023-04-30: 4676917.61; 2023-05-07: 4676917.61; 2023-05-14: 668131.09
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Actual Units
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Remaining Units | 2023-01-29: 4008786.52; 2023-02-05: 4676917.61; 2023-02-12: 4676917.61; 2023-02-19: 4676917.61; 2023-02-26: 4676917.61; 2023-03-05: 4676917.61; 2023-03-12: 4676917.61; 2023-03-19: 4676917.61; 2023-03-26: 4676917.61; 2023-04-02: 4676917.61; 2023-04-09: 3340655.44; 2023-04-23: 668131.09; 2023-04-30: 4676917.61; 2023-05-07: 4676917.61; 2023-05-14: 668131.09
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Actual Units
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Remaining Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 233718.15; 2023-04-23: 77906.05; 2023-04-30: 545342.35; 2023-05-07: 545342.35; 2023-05-14: 545342.35; 2023-05-21: 545342.35; 2023-05-28: 545342.35; 2023-06-04: 545342.35; 2023-06-11: 545342.35; 2023-06-18: 467436.3; 2023-07-02: 77906.05
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Actual Units
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Remaining Units | 2023-04-09: 233718.15; 2023-04-23: 77906.05; 2023-04-30: 545342.35; 2023-05-07: 545342.35; 2023-05-14: 545342.35; 2023-05-21: 545342.35; 2023-05-28: 545342.35; 2023-06-04: 545342.35; 2023-06-11: 545342.35; 2023-06-18: 467436.3; 2023-07-02: 77906.05
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Budgeted Units | 2023-06-11: 50546.08; 2023-06-18: 101092.16; 2023-07-02: 16848.69; 2023-07-09: 117940.86; 2023-07-16: 117940.86; 2023-07-23: 101092.16
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Actual Units
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Remaining Units | 2023-06-11: 50546.08; 2023-06-18: 101092.16; 2023-07-02: 16848.69; 2023-07-09: 117940.86; 2023-07-16: 117940.86; 2023-07-23: 101092.16
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Budgeted Units | 2023-06-11: 34015.73; 2023-06-18: 68031.47; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.47
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Actual Units
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Remaining Units | 2023-06-11: 34015.73; 2023-06-18: 68031.47; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.47
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Budgeted Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Actual Units
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Remaining Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Budgeted Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Actual Units
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Remaining Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Budgeted Units | 2023-01-22: 226741.32; 2023-01-29: 317437.85; 2023-02-05: 317437.85; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Remaining Units | 2023-01-22: 226741.32; 2023-01-29: 317437.85; 2023-02-05: 317437.85; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Budgeted Units | 2023-04-09: 164387.46; 2023-04-23: 82193.73; 2023-04-30: 575356.1
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Remaining Units | 2023-04-09: 164387.46; 2023-04-23: 82193.73; 2023-04-30: 575356.1
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Remaining Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Budgeted Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Remaining Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 98738.76; 2023-03-26: 691171.31; 2023-04-02: 691171.31; 2023-04-09: 296216.28
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Remaining Units | 2023-03-19: 98738.76; 2023-03-26: 691171.31; 2023-04-02: 691171.31; 2023-04-09: 296216.28
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Budgeted Units | 2023-06-11: 428180.37; 2023-06-18: 642270.55; 2023-07-02: 107045.09; 2023-07-09: 749315.64; 2023-07-16: 428180.37
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Remaining Units | 2023-06-11: 428180.37; 2023-06-18: 642270.55; 2023-07-02: 107045.09; 2023-07-09: 749315.64; 2023-07-16: 428180.37
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 109641.36; 2023-07-23: 255829.84; 2023-07-30: 255829.84; 2023-08-06: 73094.24
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Remaining Units | 2023-07-16: 109641.36; 2023-07-23: 255829.84; 2023-07-30: 255829.84; 2023-08-06: 73094.24
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Budgeted Units | 2023-05-14: 1618933.02; 2023-05-21: 1888755.19; 2023-05-28: 1888755.19; 2023-06-04: 1888755.19; 2023-06-11: 809466.51
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Actual Units
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Remaining Units | 2023-05-14: 1618933.02; 2023-05-21: 1888755.19; 2023-05-28: 1888755.19; 2023-06-04: 1888755.19; 2023-06-11: 809466.51
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Budgeted Units | 2023-08-06: 1362663.28; 2023-08-13: 1907728.59; 2023-08-20: 1907728.59; 2023-08-27: 817597.97
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Remaining Units | 2023-08-06: 1362663.28; 2023-08-13: 1907728.59; 2023-08-20: 1907728.59; 2023-08-27: 817597.97
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Budgeted Units | 2023-07-30: 52922.18; 2023-08-06: 15120.62
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Remaining Units | 2023-07-30: 52922.18; 2023-08-06: 15120.62
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Budgeted Units | 2023-08-06: 22895.21; 2023-08-13: 22895.21
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Remaining Units | 2023-08-06: 22895.21; 2023-08-13: 22895.21
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Budgeted Units | 2023-08-27: 197259.28; 2023-09-03: 345203.74; 2023-09-10: 345203.74; 2023-09-17: 345203.74; 2023-09-24: 147944.46
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Remaining Units | 2023-08-27: 197259.28; 2023-09-03: 345203.74; 2023-09-10: 345203.74; 2023-09-17: 345203.74; 2023-09-24: 147944.46
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 272089.58; 2023-02-19: 317437.85; 2023-02-26: 317437.85
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Remaining Units | 2023-02-12: 272089.58; 2023-02-19: 317437.85; 2023-02-26: 317437.85
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Budgeted Units | 2023-05-21: 575356.1; 2023-05-28: 246581.18
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Remaining Units | 2023-05-21: 575356.1; 2023-05-28: 246581.18
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Remaining Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 67313.83; 2023-03-26: 471196.8; 2023-04-02: 471196.8; 2023-04-09: 336569.15; 2023-04-23: 67313.83; 2023-04-30: 201941.49
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Remaining Units | 2023-03-19: 67313.83; 2023-03-26: 471196.8; 2023-04-02: 471196.8; 2023-04-09: 336569.15; 2023-04-23: 67313.83; 2023-04-30: 201941.49
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 394955.04; 2023-05-07: 691171.31; 2023-05-14: 691171.31
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Remaining Units | 2023-04-30: 394955.04; 2023-05-07: 691171.31; 2023-05-14: 691171.31
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Budgeted Units | 2023-07-23: 214090.18; 2023-07-30: 749315.64; 2023-08-06: 749315.64; 2023-08-13: 642270.55
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Remaining Units | 2023-07-23: 214090.18; 2023-07-30: 749315.64; 2023-08-06: 749315.64; 2023-08-13: 642270.55
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Budgeted Units | 2023-08-13: 36547.12; 2023-08-20: 255829.84; 2023-08-27: 255829.84; 2023-09-03: 146188.48
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Remaining Units | 2023-08-13: 36547.12; 2023-08-20: 255829.84; 2023-08-27: 255829.84; 2023-09-03: 146188.48
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Budgeted Units | 2023-06-11: 1079288.68; 2023-06-18: 1618933.02; 2023-07-02: 269822.17; 2023-07-09: 1888755.19; 2023-07-16: 1888755.19; 2023-07-23: 1349110.85
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Actual Units
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Remaining Units | 2023-06-11: 1079288.68; 2023-06-18: 1618933.02; 2023-07-02: 269822.17; 2023-07-09: 1888755.19; 2023-07-16: 1888755.19; 2023-07-23: 1349110.85
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Budgeted Units | 2023-09-03: 817597.97; 2023-09-10: 1907728.59; 2023-09-17: 1907728.59; 2023-09-24: 1362663.28
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Remaining Units | 2023-09-03: 817597.97; 2023-09-10: 1907728.59; 2023-09-17: 1907728.59; 2023-09-24: 1362663.28
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Budgeted Units | 2023-08-27: 37801.56; 2023-09-03: 30241.24
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Remaining Units | 2023-08-27: 37801.56; 2023-09-03: 30241.24
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Budgeted Units | 2023-09-03: 13737.12; 2023-09-10: 32053.29
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Remaining Units | 2023-09-03: 13737.12; 2023-09-10: 32053.29
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Budgeted Units | 2023-09-24: 98629.64; 2023-10-01: 345203.74; 2023-10-08: 345203.74; 2023-10-15: 345203.74; 2023-10-22: 246574.1
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Remaining Units | 2023-09-24: 98629.64; 2023-10-01: 345203.74; 2023-10-08: 345203.74; 2023-10-15: 345203.74; 2023-10-22: 246574.1
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 317437.85; 2023-03-12: 317437.85; 2023-03-19: 272089.58
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Remaining Units | 2023-03-05: 317437.85; 2023-03-12: 317437.85; 2023-03-19: 272089.58
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Budgeted Units | 2023-06-11: 328774.91; 2023-06-18: 493162.37
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Remaining Units | 2023-06-11: 328774.91; 2023-06-18: 493162.37
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Remaining Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 269255.32; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 403882.98
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Remaining Units | 2023-04-30: 269255.32; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 403882.98
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Budgeted Units | 2023-05-21: 98738.76; 2023-05-28: 691171.31; 2023-06-04: 691171.31; 2023-06-11: 296216.28
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Remaining Units | 2023-05-21: 98738.76; 2023-05-28: 691171.31; 2023-06-04: 691171.31; 2023-06-11: 296216.28
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Budgeted Units | 2023-08-27: 749315.64; 2023-09-03: 749315.64; 2023-09-10: 749315.64; 2023-09-17: 107045.09
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Remaining Units | 2023-08-27: 749315.64; 2023-09-03: 749315.64; 2023-09-10: 749315.64; 2023-09-17: 107045.09
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Budgeted Units | 2023-09-17: 219282.72; 2023-09-24: 255829.84; 2023-10-01: 219282.72
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Remaining Units | 2023-09-17: 219282.72; 2023-09-24: 255829.84; 2023-10-01: 219282.72
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Budgeted Units | 2023-07-23: 539644.34; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1888755.19; 2023-08-20: 1888755.19
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Actual Units
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Remaining Units | 2023-07-23: 539644.34; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1888755.19; 2023-08-20: 1888755.19
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Budgeted Units | 2023-10-01: 272532.66; 2023-10-08: 1907728.59; 2023-10-15: 1907728.59; 2023-10-22: 1907728.59
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Remaining Units | 2023-10-01: 272532.66; 2023-10-08: 1907728.59; 2023-10-15: 1907728.59; 2023-10-22: 1907728.59
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Budgeted Units | 2023-09-24: 22680.93; 2023-10-01: 45361.87
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Remaining Units | 2023-09-24: 22680.93; 2023-10-01: 45361.87
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Budgeted Units | 2023-10-01: 4579.04; 2023-10-08: 32053.29; 2023-10-15: 9158.08
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Remaining Units | 2023-10-01: 4579.04; 2023-10-08: 32053.29; 2023-10-15: 9158.08
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Budgeted Units | 2023-10-29: 345203.74; 2023-11-05: 345203.74; 2023-11-12: 345203.74; 2023-11-19: 345203.74
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Remaining Units | 2023-10-29: 345203.74; 2023-11-05: 345203.74; 2023-11-12: 345203.74; 2023-11-19: 345203.74
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 45348.26; 2023-03-26: 317437.85; 2023-04-02: 317437.85; 2023-04-09: 226741.32
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Remaining Units | 2023-03-19: 45348.26; 2023-03-26: 317437.85; 2023-04-02: 317437.85; 2023-04-09: 226741.32
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 82193.73; 2023-07-23: 575356.1; 2023-07-30: 164387.46
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Remaining Units | 2023-07-16: 82193.73; 2023-07-23: 575356.1; 2023-07-30: 164387.46
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Budgeted Units | 2023-04-23: 8502.8; 2023-04-30: 59519.6; 2023-05-07: 59519.6; 2023-05-14: 8502.8
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Remaining Units | 2023-04-23: 8502.8; 2023-04-30: 59519.6; 2023-05-07: 59519.6; 2023-05-14: 8502.8
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Budgeted Units | 2023-05-21: 67313.83; 2023-05-28: 471196.8; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 134627.66
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Remaining Units | 2023-05-21: 67313.83; 2023-05-28: 471196.8; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 134627.66
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Budgeted Units | 2023-06-18: 394955.04; 2023-07-02: 98738.76; 2023-07-09: 691171.31; 2023-07-16: 592432.55
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Remaining Units | 2023-06-18: 394955.04; 2023-07-02: 98738.76; 2023-07-09: 691171.31; 2023-07-16: 592432.55
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Budgeted Units | 2023-09-24: 535225.46; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.28
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Remaining Units | 2023-09-24: 535225.46; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.28
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Budgeted Units | 2023-10-15: 146188.48; 2023-10-22: 255829.84; 2023-10-29: 255829.84; 2023-11-05: 36547.12
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Remaining Units | 2023-10-15: 146188.48; 2023-10-22: 255829.84; 2023-10-29: 255829.84; 2023-11-05: 36547.12
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Budgeted Units | 2023-08-27: 1888755.19; 2023-09-03: 1888755.19; 2023-09-10: 1888755.19; 2023-09-17: 1888755.19; 2023-09-24: 539644.34
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Actual Units
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Remaining Units | 2023-08-27: 1888755.19; 2023-09-03: 1888755.19; 2023-09-10: 1888755.19; 2023-09-17: 1888755.19; 2023-09-24: 539644.34
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Budgeted Units | 2023-11-05: 1635195.94; 2023-11-12: 1907728.59; 2023-11-19: 1907728.59; 2023-11-26: 545065.31
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Remaining Units | 2023-11-05: 1635195.94; 2023-11-12: 1907728.59; 2023-11-19: 1907728.59; 2023-11-26: 545065.31
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Budgeted Units | 2023-10-22: 7560.31; 2023-10-29: 52922.18; 2023-11-05: 7560.31
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Remaining Units | 2023-10-22: 7560.31; 2023-10-29: 52922.18; 2023-11-05: 7560.31
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Budgeted Units | 2023-11-05: 27474.25; 2023-11-12: 18316.16
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Remaining Units | 2023-11-05: 27474.25; 2023-11-12: 18316.16
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Budgeted Units | 2023-11-26: 246574.1; 2023-12-03: 345203.74; 2023-12-10: 345203.74; 2023-12-17: 345203.74; 2023-12-24: 98629.64
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Remaining Units | 2023-11-26: 246574.1; 2023-12-03: 345203.74; 2023-12-10: 345203.74; 2023-12-17: 345203.74; 2023-12-24: 98629.64
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Budgeted Units | 2023-06-11: 458815.48; 2023-06-18: 229407.74
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Remaining Units | 2023-06-11: 458815.48; 2023-06-18: 229407.74
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Budgeted Units | 2023-08-27: 458815.48; 2023-09-03: 229407.74
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Remaining Units | 2023-08-27: 458815.48; 2023-09-03: 229407.74
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Budgeted Units | 2023-08-06: 573519.35; 2023-08-13: 114703.87
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Remaining Units | 2023-08-06: 573519.35; 2023-08-13: 114703.87
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Budgeted Units | 2023-08-13: 229407.74; 2023-08-20: 458815.48
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Remaining Units | 2023-08-13: 229407.74; 2023-08-20: 458815.48
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Budgeted Units | 2023-09-24: 458815.48; 2023-10-01: 229407.74
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Remaining Units | 2023-09-24: 458815.48; 2023-10-01: 229407.74
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Budgeted Units | 2023-07-23: 229407.74; 2023-07-30: 458815.48
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Remaining Units | 2023-07-23: 229407.74; 2023-07-30: 458815.48
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Budgeted Units | 2023-09-24: 229407.74; 2023-10-01: 458815.48
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Remaining Units | 2023-09-24: 229407.74; 2023-10-01: 458815.48
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Budgeted Units | 2023-09-03: 344111.61; 2023-09-10: 344111.61
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Remaining Units | 2023-09-03: 344111.61; 2023-09-10: 344111.61
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Budgeted Units | 2023-09-17: 688223.22
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Remaining Units | 2023-09-17: 688223.22
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Budgeted Units | 2023-10-22: 229407.74; 2023-10-29: 458815.48
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Remaining Units | 2023-10-22: 229407.74; 2023-10-29: 458815.48
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Budgeted Units | 2023-08-27: 688223.22
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Remaining Units | 2023-08-27: 688223.22
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Budgeted Units | 2023-10-29: 688223.22
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Remaining Units | 2023-10-29: 688223.22
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Budgeted Units | 2023-10-01: 114703.87; 2023-10-08: 573519.35
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Remaining Units | 2023-10-01: 114703.87; 2023-10-08: 573519.35
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Budgeted Units | 2023-10-15: 573519.35; 2023-10-22: 114703.87
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Remaining Units | 2023-10-15: 573519.35; 2023-10-22: 114703.87
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Budgeted Units | 2023-11-26: 688223.22
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Remaining Units | 2023-11-26: 688223.22
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Budgeted Units | 2023-09-24: 573519.35; 2023-10-01: 114703.87
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Remaining Units | 2023-09-24: 573519.35; 2023-10-01: 114703.87
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Budgeted Units | 2023-11-26: 573519.35; 2023-12-03: 114703.87
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Remaining Units | 2023-11-26: 573519.35; 2023-12-03: 114703.87
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Budgeted Units | 2023-11-05: 688223.22
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Remaining Units | 2023-11-05: 688223.22
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Budgeted Units | 2023-11-12: 344111.61; 2023-11-19: 344111.61
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Remaining Units | 2023-11-12: 344111.61; 2023-11-19: 344111.61
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Budgeted Units | 2023-12-24: 573519.35; 2023-12-31: 114703.87
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Remaining Units | 2023-12-24: 573519.35; 2023-12-31: 114703.87

## RES. AUG23
Project ID | Activity ID | Code [Life Cycle] | Code [Trade] | Resource ID | Spreadsheet Field | time axis 2023-01-01 to 2024-01-28
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Budgeted Units | 2023-05-28: 13720962.13; 2023-06-04: 6860481.07
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Actual Units | 2023-06-11: 20581443.2
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Budgeted Units | 2023-07-16: 6068664.8
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Actual Units | 2023-07-23: 6068664.8
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Budgeted Units | 2023-05-07: 55022560.44; 2023-05-14: 15720731.56
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Actual Units | 2023-05-21: 43793466.48; 2023-05-28: 26949825.52
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Budgeted Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Actual Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Budgeted Units | 2023-06-18: 3666166.93; 2023-07-02: 1833083.47
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Actual Units | 2023-07-23: 5499250.4
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Budgeted Units | 2023-07-23: 594660
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Actual Units | 2023-08-20: 204719.02; 2023-08-27: 389940.98
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Budgeted Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Actual Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Budgeted Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Actual Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Budgeted Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Actual Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Budgeted Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Actual Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 580190.88; 2023-05-07: 386793.92
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Actual Units | 2023-04-30: 193396.96; 2023-05-07: 676889.36; 2023-05-14: 96698.48
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Actual Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Budgeted Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Actual Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 116163.24; 2023-03-26: 813142.71; 2023-04-02: 813142.71; 2023-04-09: 348489.73
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Actual Units | 2023-03-19: 104546.92; 2023-03-26: 731828.44; 2023-04-02: 731828.44; 2023-04-09: 522734.6
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 629677.09; 2023-07-23: 881547.93; 2023-07-30: 881547.93; 2023-08-06: 377806.25
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Actual Units | 2023-07-16: 629677.09; 2023-07-23: 881547.93; 2023-07-30: 881547.93; 2023-08-06: 377806.25
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Budgeted Units | 2023-08-06: 171986.53; 2023-08-13: 300976.42; 2023-08-20: 300976.42; 2023-08-27: 42996.63
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Actual Units | 2023-08-06: 171986.53; 2023-08-13: 300976.42; 2023-08-20: 300976.42; 2023-08-27: 42996.63
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Budgeted Units | 2023-05-28: 1587189.2; 2023-06-04: 2222064.88; 2023-06-11: 2222064.88; 2023-06-18: 1904627.04; 2023-07-02: 317437.84; 2023-07-09: 1269751.36
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Actual Units | 2023-05-28: 1360447.89; 2023-06-04: 1904627.04; 2023-06-11: 1904627.04; 2023-06-18: 1632537.46; 2023-07-02: 272089.58; 2023-07-09: 1904627.04; 2023-07-16: 544179.15
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Budgeted Units | 2023-08-27: 641253.31; 2023-09-03: 2244386.58; 2023-09-10: 2244386.58; 2023-09-17: 1923759.93
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Remaining Units | 2023-08-27: 641253.31; 2023-09-03: 2244386.58; 2023-09-10: 2244386.58; 2023-09-17: 1923759.93
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Budgeted Units | 2023-08-27: 17788.98; 2023-09-03: 62261.42
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Remaining Units | 2023-08-27: 17788.98; 2023-09-03: 62261.42
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Budgeted Units | 2023-09-10: 37709.84; 2023-09-17: 16161.36
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Remaining Units | 2023-09-10: 37709.84; 2023-09-17: 16161.36
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Budgeted Units | 2023-09-17: 58017.43; 2023-09-24: 406122; 2023-10-01: 406122; 2023-10-08: 406122; 2023-10-15: 348104.57
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Remaining Units | 2023-09-17: 58017.43; 2023-09-24: 406122; 2023-10-01: 406122; 2023-10-08: 406122; 2023-10-15: 348104.57
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Actual Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Budgeted Units | 2023-07-02: 96698.48; 2023-07-09: 676889.36; 2023-07-16: 193396.96
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Actual Units | 2023-07-02: 96698.48; 2023-07-09: 676889.36; 2023-07-16: 193396.96
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Actual Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 79192.73; 2023-03-26: 554349.13; 2023-04-02: 554349.13; 2023-04-09: 395963.67; 2023-04-23: 79192.73; 2023-04-30: 237578.2
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Actual Units | 2023-03-19: 70393.54; 2023-03-26: 492754.79; 2023-04-02: 492754.79; 2023-04-09: 351967.7; 2023-04-23: 70393.54; 2023-04-30: 422361.24
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 116163.24; 2023-05-07: 813142.71; 2023-05-14: 813142.71; 2023-05-21: 348489.73
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Actual Units | 2023-04-30: 83637.54; 2023-05-07: 585462.75; 2023-05-14: 585462.75; 2023-05-21: 585462.75; 2023-05-28: 250912.61
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Budgeted Units | 2023-08-13: 377806.25; 2023-08-20: 881547.93; 2023-08-27: 881547.93; 2023-09-03: 629677.09
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Actual Units | 2023-08-13: 554115.84; 2023-08-20: 1292936.96; 2023-08-27: 923526.4
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Budgeted Units | 2023-08-27: 85993.26; 2023-09-03: 300976.42; 2023-09-10: 300976.42; 2023-09-17: 128989.89
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Remaining Units | 2023-08-27: 85993.26; 2023-09-03: 300976.42; 2023-09-10: 300976.42; 2023-09-17: 128989.89
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Budgeted Units | 2023-07-16: 1587189.2; 2023-07-23: 2222064.88; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 1269751.36
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Actual Units | 2023-07-16: 1587189.2; 2023-07-23: 2222064.88; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 1269751.36
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Budgeted Units | 2023-09-17: 1282506.62; 2023-09-24: 2244386.58; 2023-10-01: 2244386.58; 2023-10-08: 1282506.62
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Remaining Units | 2023-09-17: 1282506.62; 2023-09-24: 2244386.58; 2023-10-01: 2244386.58; 2023-10-08: 1282506.62
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Budgeted Units | 2023-09-10: 53366.93; 2023-09-17: 26683.47
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Remaining Units | 2023-09-10: 53366.93; 2023-09-17: 26683.47
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Budgeted Units | 2023-09-17: 21548.48; 2023-09-24: 32322.72
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Remaining Units | 2023-09-17: 21548.48; 2023-09-24: 32322.72
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Budgeted Units | 2023-10-08: 174052.29; 2023-10-15: 406122; 2023-10-22: 406122; 2023-10-29: 406122; 2023-11-05: 232069.71
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Remaining Units | 2023-10-08: 174052.29; 2023-10-15: 406122; 2023-10-22: 406122; 2023-10-29: 406122; 2023-11-05: 232069.71
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Actual Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Budgeted Units | 2023-06-11: 96698.48; 2023-06-18: 580190.88; 2023-07-02: 96698.48; 2023-07-09: 193396.96
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Actual Units | 2023-06-11: 138140.69; 2023-06-18: 828844.11
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Actual Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 79192.73; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 554349.13; 2023-05-28: 158385.47
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Actual Units | 2023-04-30: 79192.73; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 554349.13; 2023-05-28: 158385.47
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Budgeted Units | 2023-05-28: 580816.22; 2023-06-04: 813142.71; 2023-06-11: 696979.47
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Actual Units | 2023-05-28: 491985.51; 2023-06-04: 860974.64; 2023-06-11: 737978.26
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Budgeted Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Remaining Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Budgeted Units | 2023-10-15: 171986.53; 2023-10-22: 300976.42; 2023-10-29: 300976.42; 2023-11-05: 42996.63
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Remaining Units | 2023-10-15: 171986.53; 2023-10-22: 300976.42; 2023-10-29: 300976.42; 2023-11-05: 42996.63
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Budgeted Units | 2023-08-13: 952313.52; 2023-08-20: 2222064.88; 2023-08-27: 2222064.88; 2023-09-03: 2222064.88; 2023-09-10: 1904627.04
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Actual Units | 2023-08-27: 1904627
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Remaining Units | 2023-08-27: 7618508.2
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Budgeted Units | 2023-11-05: 1923759.93; 2023-11-12: 2244386.58; 2023-11-19: 2244386.58; 2023-11-26: 641253.31
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Remaining Units | 2023-11-05: 1923759.93; 2023-11-12: 2244386.58; 2023-11-19: 2244386.58; 2023-11-26: 641253.31
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Budgeted Units | 2023-10-22: 8894.49; 2023-10-29: 62261.42; 2023-11-05: 8894.49
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Remaining Units | 2023-10-22: 8894.49; 2023-10-29: 62261.42; 2023-11-05: 8894.49
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Budgeted Units | 2023-11-05: 32322.72; 2023-11-12: 21548.48
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Remaining Units | 2023-11-05: 32322.72; 2023-11-12: 21548.48
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Budgeted Units | 2023-11-26: 290087.14; 2023-12-03: 406122; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 116034.86
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Remaining Units | 2023-11-26: 290087.14; 2023-12-03: 406122; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 116034.86
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Actual Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 483492.4; 2023-07-23: 483492.4
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Actual Units | 2023-07-16: 345351.71; 2023-07-23: 483492.4; 2023-07-30: 138140.69
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 60019.8; 2023-05-07: 70023.1; 2023-05-14: 30009.9
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Actual Units | 2023-04-30: 60019.8; 2023-05-07: 70023.1; 2023-05-14: 30009.9
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Budgeted Units | 2023-05-28: 395963.67; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 395963.67
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Actual Units | 2023-05-28: 395963.67; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 395963.67
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Budgeted Units | 2023-06-18: 116163.24; 2023-07-02: 116163.24; 2023-07-09: 813142.71; 2023-07-16: 813142.71; 2023-07-23: 232326.49
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Actual Units | 2023-06-18: 190085.31; 2023-07-02: 190085.31; 2023-07-09: 1330597.16; 2023-07-16: 380170.62
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Budgeted Units | 2023-10-22: 377806.25; 2023-10-29: 881547.93; 2023-11-05: 881547.93; 2023-11-12: 629677.09
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Remaining Units | 2023-10-22: 377806.25; 2023-10-29: 881547.93; 2023-11-05: 881547.93; 2023-11-12: 629677.09
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Budgeted Units | 2023-11-12: 85993.26; 2023-11-19: 300976.42; 2023-11-26: 300976.42; 2023-12-03: 128989.89
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Remaining Units | 2023-11-12: 85993.26; 2023-11-19: 300976.42; 2023-11-26: 300976.42; 2023-12-03: 128989.89
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Budgeted Units | 2023-09-24: 1587189.2; 2023-10-01: 2222064.88; 2023-10-08: 2222064.88; 2023-10-15: 2222064.88; 2023-10-22: 1269751.36
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Actual Units
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Remaining Units | 2023-09-24: 1587189.2; 2023-10-01: 2222064.88; 2023-10-08: 2222064.88; 2023-10-15: 2222064.88; 2023-10-22: 1269751.36
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Budgeted Units | 2023-12-03: 1282506.62; 2023-12-10: 2244386.58; 2023-12-17: 2244386.58; 2023-12-24: 1282506.62
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Remaining Units | 2023-12-03: 1282506.62; 2023-12-10: 2244386.58; 2023-12-17: 2244386.58; 2023-12-24: 1282506.62
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Budgeted Units | 2023-11-26: 53366.93; 2023-12-03: 26683.47
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Remaining Units | 2023-11-26: 53366.93; 2023-12-03: 26683.47
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Budgeted Units | 2023-12-03: 21548.48; 2023-12-10: 32322.72
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Remaining Units | 2023-12-03: 21548.48; 2023-12-10: 32322.72
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Budgeted Units | 2023-12-24: 174052.29; 2023-12-31: 406122; 2024-01-07: 406122; 2024-01-14: 406122; 2024-01-21: 232069.71
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Remaining Units | 2023-12-24: 174052.29; 2023-12-31: 406122; 2024-01-07: 406122; 2024-01-14: 406122; 2024-01-21: 232069.71
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Budgeted Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Actual Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Remaining Units
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Budgeted Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Actual Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Budgeted Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Actual Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Actual Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Actual Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-08: 589905.6; 2023-01-15: 196635.2
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Actual Units | 2023-01-08: 589905.6; 2023-01-15: 196635.2
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 131090.13; 2023-01-08: 655450.67
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Actual Units | 2023-01-01: 131090.13; 2023-01-08: 655450.67
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 561814.86; 2023-01-22: 224725.94
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Actual Units | 2023-01-15: 561814.86; 2023-01-22: 224725.94
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 327725.33; 2023-01-29: 458815.47
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Actual Units | 2023-01-22: 327725.33; 2023-01-29: 458815.47
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Actual Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Actual Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 157308.16; 2023-01-08: 629232.64
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Actual Units | 2023-01-01: 157308.16; 2023-01-08: 629232.64
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-08: 674177.83; 2023-01-15: 112362.97
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Actual Units | 2023-01-08: 674177.83; 2023-01-15: 112362.97
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-15: 491588; 2023-01-22: 294952.8
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Actual Units | 2023-01-15: 491588; 2023-01-22: 294952.8
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 262180.27; 2023-01-15: 524360.53
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Actual Units | 2023-01-08: 262180.27; 2023-01-15: 524360.53
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 449451.89; 2023-01-29: 337088.91
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Actual Units | 2023-01-22: 449451.89; 2023-01-29: 337088.91
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 262180.27; 2023-02-05: 458815.47; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Actual Units | 2023-01-29: 262180.27; 2023-02-05: 458815.47; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Actual Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Actual Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Actual Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-15: 674177.83; 2023-01-22: 112362.97
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Actual Units | 2023-01-15: 674177.83; 2023-01-22: 112362.97
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-22: 393270.4; 2023-01-29: 393270.4
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Actual Units | 2023-01-22: 393270.4; 2023-01-29: 393270.4
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 393270.4; 2023-01-22: 393270.4
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Actual Units | 2023-01-15: 393270.4; 2023-01-22: 393270.4
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 337088.91; 2023-02-05: 449451.89
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Actual Units | 2023-01-29: 337088.91; 2023-02-05: 449451.89
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 196635.2; 2023-02-12: 458815.47; 2023-02-19: 131090.13
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Actual Units | 2023-02-05: 196635.2; 2023-02-12: 458815.47; 2023-02-19: 131090.13
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Actual Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Actual Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 786540.8
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Actual Units | 2023-01-15: 786540.8
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-22: 674177.83; 2023-01-29: 112362.97
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Actual Units | 2023-01-22: 674177.83; 2023-01-29: 112362.97
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-29: 294952.8; 2023-02-05: 491588
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Actual Units | 2023-01-29: 294952.8; 2023-02-05: 491588
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 524360.53; 2023-01-29: 262180.27
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Actual Units | 2023-01-22: 524360.53; 2023-01-29: 262180.27
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 224725.94; 2023-02-12: 561814.86
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Actual Units | 2023-02-05: 224725.94; 2023-02-12: 561814.86
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-12: 131090.13; 2023-02-19: 458815.47; 2023-02-26: 196635.2
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Actual Units | 2023-02-12: 131090.13; 2023-02-19: 458815.47; 2023-02-26: 196635.2
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Actual Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Actual Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Budgeted Units | 2023-03-19: 1166281.77; 2023-03-26: 2040993.09; 2023-04-02: 2040993.09; 2023-04-09: 1457852.21; 2023-04-23: 291570.44; 2023-04-30: 2040993.09; 2023-05-07: 2040993.09; 2023-05-14: 2040993.09; 2023-05-21: 2040993.09; 2023-05-28: 2040993.09; 2023-06-04: 291570.44
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Actual Units | 2023-03-19: 999670.09; 2023-03-26: 1749422.65; 2023-04-02: 1749422.65; 2023-04-09: 1249587.61; 2023-04-23: 249917.52; 2023-04-30: 1749422.65; 2023-05-07: 1749422.65; 2023-05-14: 1749422.65; 2023-05-21: 1749422.65; 2023-05-28: 1749422.65; 2023-06-04: 1749422.65; 2023-06-11: 999670.09
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Budgeted Units | 2023-04-30: 85972.75; 2023-05-07: 601809.25; 2023-05-14: 601809.25; 2023-05-21: 601809.25; 2023-05-28: 601809.25; 2023-06-04: 601809.25; 2023-06-11: 601809.25; 2023-06-18: 515836.5; 2023-07-02: 85972.75; 2023-07-09: 601809.25; 2023-07-16: 257918.25
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Actual Units | 2023-04-30: 73690.93; 2023-05-07: 515836.5; 2023-05-14: 515836.5; 2023-05-21: 515836.5; 2023-05-28: 515836.5; 2023-06-04: 515836.5; 2023-06-11: 515836.5; 2023-06-18: 442145.57; 2023-07-02: 73690.93; 2023-07-09: 515836.5; 2023-07-16: 515836.5; 2023-07-23: 442145.57
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Budgeted Units | 2023-01-29: 4008786.53; 2023-02-05: 4676917.61; 2023-02-12: 4676917.61; 2023-02-19: 4676917.61; 2023-02-26: 4676917.61; 2023-03-05: 4676917.61; 2023-03-12: 4676917.61; 2023-03-19: 4676917.61; 2023-03-26: 4676917.61; 2023-04-02: 4676917.61; 2023-04-09: 3340655.44; 2023-04-23: 668131.09; 2023-04-30: 4676917.61; 2023-05-07: 4676917.61; 2023-05-14: 668131.09
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Actual Units | 2023-01-29: 3436102.74; 2023-02-05: 4008786.53; 2023-02-12: 4008786.53; 2023-02-19: 4008786.53; 2023-02-26: 4008786.53; 2023-03-05: 4008786.53; 2023-03-12: 4008786.53; 2023-03-19: 4008786.53; 2023-03-26: 4008786.53; 2023-04-02: 4008786.53; 2023-04-09: 2863418.95; 2023-04-23: 572683.79; 2023-04-30: 4008786.53; 2023-05-07: 4008786.53; 2023-05-14: 4008786.53; 2023-05-21: 4008786.53; 2023-05-28: 1145367.58
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Actual Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 233718.15; 2023-04-23: 77906.05; 2023-04-30: 545342.35; 2023-05-07: 545342.35; 2023-05-14: 545342.35; 2023-05-21: 545342.35; 2023-05-28: 545342.35; 2023-06-04: 545342.35; 2023-06-11: 545342.35; 2023-06-18: 467436.3; 2023-07-02: 77906.05
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Actual Units | 2023-04-09: 175288.61; 2023-04-23: 58429.54; 2023-04-30: 409006.76; 2023-05-07: 409006.76; 2023-05-14: 409006.76; 2023-05-21: 409006.76; 2023-05-28: 409006.76; 2023-06-04: 409006.76; 2023-06-11: 409006.76; 2023-06-18: 350577.23; 2023-07-02: 58429.54; 2023-07-09: 409006.76; 2023-07-16: 409006.76; 2023-07-23: 350577.22
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Budgeted Units | 2023-06-11: 50546.08; 2023-06-18: 101092.16; 2023-07-02: 16848.69; 2023-07-09: 117940.85; 2023-07-16: 117940.85; 2023-07-23: 101092.16
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Actual Units | 2023-06-11: 24858.73; 2023-06-18: 49717.46; 2023-07-02: 8286.24; 2023-07-09: 58003.7; 2023-07-16: 58003.7; 2023-07-23: 58003.7; 2023-07-30: 58003.7; 2023-08-06: 58003.7; 2023-08-13: 58003.7; 2023-08-20: 58003.7; 2023-08-27: 16572.49
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Budgeted Units | 2023-06-11: 34015.73; 2023-06-18: 68031.46; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.46
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Actual Units | 2023-06-11: 34015.73; 2023-06-18: 68031.46; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.46
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Budgeted Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Actual Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Budgeted Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Actual Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Budgeted Units | 2023-01-22: 226741.33; 2023-01-29: 317437.86; 2023-02-05: 317437.86; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Actual Units | 2023-01-22: 226741.33; 2023-01-29: 317437.86; 2023-02-05: 317437.86; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 493162.38; 2023-05-07: 328774.92
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Actual Units | 2023-04-30: 164387.46; 2023-05-07: 575356.11; 2023-05-14: 82193.73
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Actual Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Budgeted Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Actual Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 98738.76; 2023-03-26: 691171.33; 2023-04-02: 691171.33; 2023-04-09: 296216.28
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Actual Units | 2023-03-19: 88864.89; 2023-03-26: 622054.2; 2023-04-02: 622054.2; 2023-04-09: 444324.43
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 535225.45; 2023-07-23: 749315.64; 2023-07-30: 749315.64; 2023-08-06: 321135.27
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Actual Units | 2023-07-16: 535225.45; 2023-07-23: 749315.64; 2023-07-30: 749315.64; 2023-08-06: 321135.27
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Budgeted Units | 2023-08-06: 146188.48; 2023-08-13: 255829.85; 2023-08-20: 255829.85; 2023-08-27: 36547.12
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Actual Units | 2023-08-06: 146188.48; 2023-08-13: 255829.85; 2023-08-20: 255829.85; 2023-08-27: 36547.12
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Budgeted Units | 2023-05-28: 1349110.85; 2023-06-04: 1888755.19; 2023-06-11: 1888755.19; 2023-06-18: 1618933.02; 2023-07-02: 269822.17; 2023-07-09: 1079288.68
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Actual Units | 2023-05-28: 1156380.73; 2023-06-04: 1618933.02; 2023-06-11: 1618933.02; 2023-06-18: 1387656.87; 2023-07-02: 231276.15; 2023-07-09: 1618933.02; 2023-07-16: 462552.29
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Budgeted Units | 2023-08-27: 545065.31; 2023-09-03: 1907728.58; 2023-09-10: 1907728.58; 2023-09-17: 1635195.93
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Remaining Units | 2023-08-27: 545065.31; 2023-09-03: 1907728.58; 2023-09-10: 1907728.58; 2023-09-17: 1635195.93
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Budgeted Units | 2023-08-27: 15120.62; 2023-09-03: 52922.18
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Remaining Units | 2023-08-27: 15120.62; 2023-09-03: 52922.18
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Budgeted Units | 2023-09-10: 32053.28; 2023-09-17: 13737.12
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Remaining Units | 2023-09-10: 32053.28; 2023-09-17: 13737.12
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Budgeted Units | 2023-09-17: 49314.82; 2023-09-24: 345203.75; 2023-10-01: 345203.75; 2023-10-08: 345203.75; 2023-10-15: 295888.93
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Remaining Units | 2023-09-17: 49314.82; 2023-09-24: 345203.75; 2023-10-01: 345203.75; 2023-10-08: 345203.75; 2023-10-15: 295888.93
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 272089.59; 2023-02-19: 317437.86; 2023-02-26: 317437.86
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Actual Units | 2023-02-12: 272089.59; 2023-02-19: 317437.86; 2023-02-26: 317437.86
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Budgeted Units | 2023-07-02: 82193.73; 2023-07-09: 575356.11; 2023-07-16: 164387.46
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Actual Units | 2023-07-02: 82193.73; 2023-07-09: 575356.11; 2023-07-16: 164387.46
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Actual Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 67313.83; 2023-03-26: 471196.8; 2023-04-02: 471196.8; 2023-04-09: 336569.15; 2023-04-23: 67313.83; 2023-04-30: 201941.49
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Actual Units | 2023-03-19: 59834.51; 2023-03-26: 418841.6; 2023-04-02: 418841.6; 2023-04-09: 299172.57; 2023-04-23: 59834.51; 2023-04-30: 359007.09
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 98738.76; 2023-05-07: 691171.33; 2023-05-14: 691171.33; 2023-05-21: 296216.28
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Actual Units | 2023-04-30: 71091.91; 2023-05-07: 497643.36; 2023-05-14: 497643.36; 2023-05-21: 497643.36; 2023-05-28: 213275.72
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Budgeted Units | 2023-08-13: 321135.27; 2023-08-20: 749315.64; 2023-08-27: 749315.64; 2023-09-03: 535225.45
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Actual Units | 2023-08-13: 470998.4; 2023-08-20: 1098996.27; 2023-08-27: 784997.33
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Budgeted Units | 2023-08-27: 73094.24; 2023-09-03: 255829.85; 2023-09-10: 255829.85; 2023-09-17: 109641.36
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Remaining Units | 2023-08-27: 73094.24; 2023-09-03: 255829.85; 2023-09-10: 255829.85; 2023-09-17: 109641.36
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Budgeted Units | 2023-07-16: 1349110.85; 2023-07-23: 1888755.19; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1079288.68
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Actual Units | 2023-07-16: 1349110.85; 2023-07-23: 1888755.19; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1079288.68
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Budgeted Units | 2023-09-17: 1090130.62; 2023-09-24: 1907728.58; 2023-10-01: 1907728.58; 2023-10-08: 1090130.62
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Remaining Units | 2023-09-17: 1090130.62; 2023-09-24: 1907728.58; 2023-10-01: 1907728.58; 2023-10-08: 1090130.62
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Budgeted Units | 2023-09-10: 45361.87; 2023-09-17: 22680.93
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Remaining Units | 2023-09-10: 45361.87; 2023-09-17: 22680.93
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Budgeted Units | 2023-09-17: 18316.16; 2023-09-24: 27474.24
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Remaining Units | 2023-09-17: 18316.16; 2023-09-24: 27474.24
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Budgeted Units | 2023-10-08: 147944.46; 2023-10-15: 345203.75; 2023-10-22: 345203.75; 2023-10-29: 345203.75; 2023-11-05: 197259.29
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Remaining Units | 2023-10-08: 147944.46; 2023-10-15: 345203.75; 2023-10-22: 345203.75; 2023-10-29: 345203.75; 2023-11-05: 197259.29
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 317437.86; 2023-03-12: 317437.86; 2023-03-19: 272089.59
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Actual Units | 2023-03-05: 317437.86; 2023-03-12: 317437.86; 2023-03-19: 272089.59
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Budgeted Units | 2023-06-11: 82193.73; 2023-06-18: 493162.38; 2023-07-02: 82193.73; 2023-07-09: 164387.46
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Actual Units | 2023-06-11: 117419.61; 2023-06-18: 704517.69
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Actual Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 67313.83; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 471196.8; 2023-05-28: 134627.66
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Actual Units | 2023-04-30: 67313.83; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 471196.8; 2023-05-28: 134627.66
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Budgeted Units | 2023-05-28: 493693.81; 2023-06-04: 691171.33; 2023-06-11: 592432.57
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Actual Units | 2023-05-28: 418187.69; 2023-06-04: 731828.46; 2023-06-11: 627281.54
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Budgeted Units | 2023-09-24: 535225.45; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.27
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Remaining Units | 2023-09-24: 535225.45; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.27
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Budgeted Units | 2023-10-15: 146188.48; 2023-10-22: 255829.85; 2023-10-29: 255829.85; 2023-11-05: 36547.12
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Remaining Units | 2023-10-15: 146188.48; 2023-10-22: 255829.85; 2023-10-29: 255829.85; 2023-11-05: 36547.12
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Budgeted Units | 2023-08-13: 809466.51; 2023-08-20: 1888755.19; 2023-08-27: 1888755.19; 2023-09-03: 1888755.19; 2023-09-10: 1618933.02
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Actual Units | 2023-08-27: 1618933.02
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Remaining Units | 2023-08-27: 6475732.08
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Budgeted Units | 2023-11-05: 1635195.93; 2023-11-12: 1907728.58; 2023-11-19: 1907728.58; 2023-11-26: 545065.31
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Remaining Units | 2023-11-05: 1635195.93; 2023-11-12: 1907728.58; 2023-11-19: 1907728.58; 2023-11-26: 545065.31
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Budgeted Units | 2023-10-22: 7560.31; 2023-10-29: 52922.18; 2023-11-05: 7560.31
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Remaining Units | 2023-10-22: 7560.31; 2023-10-29: 52922.18; 2023-11-05: 7560.31
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Budgeted Units | 2023-11-05: 27474.24; 2023-11-12: 18316.16
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Remaining Units | 2023-11-05: 27474.24; 2023-11-12: 18316.16
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Budgeted Units | 2023-11-26: 246574.11; 2023-12-03: 345203.75; 2023-12-10: 345203.75; 2023-12-17: 345203.75; 2023-12-24: 98629.64
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Remaining Units | 2023-11-26: 246574.11; 2023-12-03: 345203.75; 2023-12-10: 345203.75; 2023-12-17: 345203.75; 2023-12-24: 98629.64
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 45348.27; 2023-03-26: 317437.86; 2023-04-02: 317437.86; 2023-04-09: 226741.33
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Actual Units | 2023-03-19: 45348.27; 2023-03-26: 317437.86; 2023-04-02: 317437.86; 2023-04-09: 226741.33
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 410968.65; 2023-07-23: 410968.65
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Actual Units | 2023-07-16: 293549.04; 2023-07-23: 410968.65; 2023-07-30: 117419.61
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 51016.8; 2023-05-07: 59519.6; 2023-05-14: 25508.4
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Actual Units | 2023-04-30: 51016.8; 2023-05-07: 59519.6; 2023-05-14: 25508.4
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Budgeted Units | 2023-05-28: 336569.15; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 336569.15
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Actual Units | 2023-05-28: 336569.15; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 336569.15
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Budgeted Units | 2023-06-18: 98738.76; 2023-07-02: 98738.76; 2023-07-09: 691171.33; 2023-07-16: 691171.33; 2023-07-23: 197477.52
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Actual Units | 2023-06-18: 161572.52; 2023-07-02: 161572.52; 2023-07-09: 1131007.63; 2023-07-16: 323145.04
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Budgeted Units | 2023-10-22: 321135.27; 2023-10-29: 749315.64; 2023-11-05: 749315.64; 2023-11-12: 535225.45
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Remaining Units | 2023-10-22: 321135.27; 2023-10-29: 749315.64; 2023-11-05: 749315.64; 2023-11-12: 535225.45
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Budgeted Units | 2023-11-12: 73094.24; 2023-11-19: 255829.85; 2023-11-26: 255829.85; 2023-12-03: 109641.36
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Remaining Units | 2023-11-12: 73094.24; 2023-11-19: 255829.85; 2023-11-26: 255829.85; 2023-12-03: 109641.36
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Budgeted Units | 2023-09-24: 1349110.85; 2023-10-01: 1888755.19; 2023-10-08: 1888755.19; 2023-10-15: 1888755.19; 2023-10-22: 1079288.68
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Actual Units
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Remaining Units | 2023-09-24: 1349110.85; 2023-10-01: 1888755.19; 2023-10-08: 1888755.19; 2023-10-15: 1888755.19; 2023-10-22: 1079288.68
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Budgeted Units | 2023-12-03: 1090130.62; 2023-12-10: 1907728.58; 2023-12-17: 1907728.58; 2023-12-24: 1090130.62
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Remaining Units | 2023-12-03: 1090130.62; 2023-12-10: 1907728.58; 2023-12-17: 1907728.58; 2023-12-24: 1090130.62
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Budgeted Units | 2023-11-26: 45361.87; 2023-12-03: 22680.93
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Remaining Units | 2023-11-26: 45361.87; 2023-12-03: 22680.93
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Budgeted Units | 2023-12-03: 18316.16; 2023-12-10: 27474.24
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Remaining Units | 2023-12-03: 18316.16; 2023-12-10: 27474.24
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Budgeted Units | 2023-12-24: 147944.46; 2023-12-31: 345203.75; 2024-01-07: 345203.75; 2024-01-14: 345203.75; 2024-01-21: 197259.29
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Remaining Units | 2023-12-24: 147944.46; 2023-12-31: 345203.75; 2024-01-07: 345203.75; 2024-01-14: 345203.75; 2024-01-21: 197259.29
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Budgeted Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Remaining Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Budgeted Units | 2023-09-17: 114703.87; 2023-09-24: 573519.33
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Remaining Units | 2023-09-17: 114703.87; 2023-09-24: 573519.33
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Budgeted Units | 2023-09-10: 688223.2
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Remaining Units | 2023-09-10: 688223.2
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Budgeted Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Remaining Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Budgeted Units | 2023-10-15: 114703.87; 2023-10-22: 573519.33
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Remaining Units | 2023-10-15: 114703.87; 2023-10-22: 573519.33
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Budgeted Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Remaining Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Budgeted Units | 2023-10-08: 344111.6; 2023-10-15: 344111.6
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Remaining Units | 2023-10-08: 344111.6; 2023-10-15: 344111.6
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Budgeted Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Remaining Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Budgeted Units | 2023-09-24: 114703.87; 2023-10-01: 573519.33
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Remaining Units | 2023-09-24: 114703.87; 2023-10-01: 573519.33
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Budgeted Units | 2023-11-05: 344111.6; 2023-11-12: 344111.6
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Remaining Units | 2023-11-05: 344111.6; 2023-11-12: 344111.6
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Budgeted Units | 2023-09-24: 573519.33; 2023-10-01: 114703.87
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Remaining Units | 2023-09-24: 573519.33; 2023-10-01: 114703.87
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Budgeted Units | 2023-11-26: 573519.33; 2023-12-03: 114703.87
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Remaining Units | 2023-11-26: 573519.33; 2023-12-03: 114703.87
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Budgeted Units | 2023-11-05: 688223.2
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Remaining Units | 2023-11-05: 688223.2
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Budgeted Units | 2023-11-12: 344111.6; 2023-11-19: 344111.6
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Remaining Units | 2023-11-12: 344111.6; 2023-11-19: 344111.6
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Budgeted Units | 2023-12-24: 573519.33; 2023-12-31: 114703.87
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Remaining Units | 2023-12-24: 573519.33; 2023-12-31: 114703.87
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Budgeted Units | 2023-10-22: 344111.6; 2023-10-29: 344111.6
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Remaining Units | 2023-10-22: 344111.6; 2023-10-29: 344111.6
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Budgeted Units | 2023-12-24: 344111.6; 2023-12-31: 344111.6
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Remaining Units | 2023-12-24: 344111.6; 2023-12-31: 344111.6
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Budgeted Units | 2023-12-03: 458815.47; 2023-12-10: 229407.73
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Remaining Units | 2023-12-03: 458815.47; 2023-12-10: 229407.73
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Budgeted Units | 2023-12-10: 114703.87; 2023-12-17: 573519.33
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Remaining Units | 2023-12-10: 114703.87; 2023-12-17: 573519.33
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Budgeted Units | 2024-01-21: 344111.6; 2024-01-28: 344111.6
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Remaining Units | 2024-01-21: 344111.6; 2024-01-28: 344111.6

## RES. OCT23
Project ID | Activity ID | Code [Life Cycle] | Code [Trade] | Resource ID | Spreadsheet Field | time axis 2023-01-01 to 2024-02-04
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Budgeted Units | 2023-05-28: 13720962.13; 2023-06-04: 6860481.07
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Actual Units | 2023-06-11: 20581443.2
PCS_PJ02 | PC.GE.0010 | PC | CV | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Budgeted Units | 2023-07-16: 6068664.8
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Actual Units | 2023-07-23: 6068664.8
PCS_PJ02 | PC.GE.0020 | PC | CV | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Budgeted Units | 2023-05-07: 55022560.44; 2023-05-14: 15720731.56
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Actual Units | 2023-05-21: 43793466.48; 2023-05-28: 26949825.52
PCS_PJ02 | PC.GE.0030 | PC | MC | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Budgeted Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Actual Units | 2023-07-30: 26055725.33; 2023-08-06: 20844580.27
PCS_PJ02 | PC.GE.0040 | PC | EL | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Budgeted Units | 2023-06-18: 3666166.93; 2023-07-02: 1833083.47
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Actual Units | 2023-07-23: 5499250.4
PCS_PJ02 | PC.GE.0050 | PC | EL | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Budgeted Units | 2023-07-23: 594660
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Actual Units | 2023-08-20: 204719.02; 2023-08-27: 389940.98
PCS_PJ02 | PC.GE.0060 | PC | ME | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Budgeted Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Actual Units | 2023-07-23: 400184.8
PCS_PJ02 | PC.GE.0070 | PC | MM | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Budgeted Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Actual Units | 2023-08-06: 4371866; 2023-08-13: 4371866
PCS_PJ02 | PC.GE.0080 | PC | CP | EVSV | Remaining Units
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Budgeted Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Actual Units | 2023-07-30: 1846608; 2023-08-06: 1477286.4
PCS_PJ02 | PC.GE.0090 | PC | CP | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Budgeted Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Actual Units | 2023-01-22: 266754.4; 2023-01-29: 373456.16; 2023-02-05: 373456.16; 2023-02-12: 53350.88
PCS_PJ02 | CN.C1.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 580190.88; 2023-05-07: 386793.92
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Actual Units | 2023-04-30: 193396.96; 2023-05-07: 676889.36; 2023-05-14: 96698.48
PCS_PJ02 | CN.C1.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Actual Units | 2023-02-12: 60019.8; 2023-02-19: 70023.1; 2023-02-26: 30009.9
PCS_PJ02 | CN.C1.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Budgeted Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Actual Units | 2023-02-26: 316770.93; 2023-03-05: 554349.13; 2023-03-12: 554349.13; 2023-03-19: 475156.4
PCS_PJ02 | CN.C1.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 116163.24; 2023-03-26: 813142.71; 2023-04-02: 813142.71; 2023-04-09: 348489.73
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Actual Units | 2023-03-19: 104546.92; 2023-03-26: 731828.44; 2023-04-02: 731828.44; 2023-04-09: 522734.6
PCS_PJ02 | CN.C1.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 629677.09; 2023-07-23: 881547.93; 2023-07-30: 881547.93; 2023-08-06: 377806.25
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Actual Units | 2023-07-16: 629677.09; 2023-07-23: 881547.93; 2023-07-30: 881547.93; 2023-08-06: 377806.25
PCS_PJ02 | CN.C1.0060 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Budgeted Units | 2023-08-06: 171986.53; 2023-08-13: 300976.42; 2023-08-20: 300976.42; 2023-08-27: 42996.63
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Actual Units | 2023-08-06: 171986.53; 2023-08-13: 300976.42; 2023-08-20: 300976.42; 2023-08-27: 42996.63
PCS_PJ02 | CN.C1.0070 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Budgeted Units | 2023-05-28: 1587189.2; 2023-06-04: 2222064.88; 2023-06-11: 2222064.88; 2023-06-18: 1904627.04; 2023-07-02: 317437.84; 2023-07-09: 1269751.36
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Actual Units | 2023-05-28: 1360447.89; 2023-06-04: 1904627.04; 2023-06-11: 1904627.04; 2023-06-18: 1632537.46; 2023-07-02: 272089.58; 2023-07-09: 1904627.04; 2023-07-16: 544179.15
PCS_PJ02 | CN.C1.0080 | CN | MC | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Budgeted Units | 2023-08-27: 641253.31; 2023-09-03: 2244386.58; 2023-09-10: 2244386.58; 2023-09-17: 1923759.93
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Actual Units | 2023-08-27: 641253.31; 2023-09-03: 2244386.58; 2023-09-10: 2244386.58; 2023-09-17: 1923759.93
PCS_PJ02 | CN.C1.0090 | CN | EL | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Budgeted Units | 2023-08-27: 17788.98; 2023-09-03: 62261.42
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Actual Units | 2023-08-27: 17788.98; 2023-09-03: 62261.42
PCS_PJ02 | CN.C1.0100 | CN | ME | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Budgeted Units | 2023-09-10: 37709.84; 2023-09-17: 16161.36
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Actual Units | 2023-09-10: 37709.84; 2023-09-17: 16161.36
PCS_PJ02 | CN.C1.0110 | CN | MM | EVSV | Remaining Units
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Budgeted Units | 2023-09-17: 58017.43; 2023-09-24: 406122; 2023-10-01: 406122; 2023-10-08: 406122; 2023-10-15: 348104.57
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Actual Units | 2023-09-17: 37488.18; 2023-09-24: 262417.29; 2023-10-01: 262417.29; 2023-10-08: 262417.29; 2023-10-15: 262417.29; 2023-10-22: 262417.29; 2023-10-29: 112464.55
PCS_PJ02 | CN.C1.0120 | CN | CP | EVSV | Remaining Units | 2023-10-29: 162448.8
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Budgeted Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Actual Units | 2023-02-12: 320105.28; 2023-02-19: 373456.16; 2023-02-26: 373456.16
PCS_PJ02 | CN.C2.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Budgeted Units | 2023-07-02: 96698.48; 2023-07-09: 676889.36; 2023-07-16: 193396.96
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Actual Units | 2023-07-02: 96698.48; 2023-07-09: 676889.36; 2023-07-16: 193396.96
PCS_PJ02 | CN.C2.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Actual Units | 2023-03-05: 70023.1; 2023-03-12: 70023.1; 2023-03-19: 20006.6
PCS_PJ02 | CN.C2.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 79192.73; 2023-03-26: 554349.13; 2023-04-02: 554349.13; 2023-04-09: 395963.67; 2023-04-23: 79192.73; 2023-04-30: 237578.2
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Actual Units | 2023-03-19: 70393.54; 2023-03-26: 492754.79; 2023-04-02: 492754.79; 2023-04-09: 351967.7; 2023-04-23: 70393.54; 2023-04-30: 422361.24
PCS_PJ02 | CN.C2.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 116163.24; 2023-05-07: 813142.71; 2023-05-14: 813142.71; 2023-05-21: 348489.73
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Actual Units | 2023-04-30: 83637.54; 2023-05-07: 585462.75; 2023-05-14: 585462.75; 2023-05-21: 585462.75; 2023-05-28: 250912.61
PCS_PJ02 | CN.C2.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Budgeted Units | 2023-08-13: 377806.25; 2023-08-20: 881547.93; 2023-08-27: 881547.93; 2023-09-03: 629677.09
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Actual Units | 2023-08-13: 554115.84; 2023-08-20: 1292936.96; 2023-08-27: 923526.4
PCS_PJ02 | CN.C2.0060 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Budgeted Units | 2023-08-27: 85993.26; 2023-09-03: 300976.42; 2023-09-10: 300976.42; 2023-09-17: 128989.89
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Actual Units | 2023-08-27: 85993.26; 2023-09-03: 300976.42; 2023-09-10: 300976.42; 2023-09-17: 128989.89
PCS_PJ02 | CN.C2.0070 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Budgeted Units | 2023-07-16: 1587189.2; 2023-07-23: 2222064.88; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 1269751.36
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Actual Units | 2023-07-16: 1587189.2; 2023-07-23: 2222064.88; 2023-07-30: 2222064.88; 2023-08-06: 2222064.88; 2023-08-13: 1269751.36
PCS_PJ02 | CN.C2.0080 | CN | MC | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Budgeted Units | 2023-09-17: 1282506.62; 2023-09-24: 2244386.58; 2023-10-01: 2244386.58; 2023-10-08: 1282506.62
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Actual Units | 2023-09-17: 1282506.62; 2023-09-24: 2244386.58; 2023-10-01: 2244386.58; 2023-10-08: 1282506.62
PCS_PJ02 | CN.C2.0090 | CN | EL | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Budgeted Units | 2023-09-10: 53366.93; 2023-09-17: 26683.47
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Actual Units | 2023-09-10: 53366.93; 2023-09-17: 26683.47
PCS_PJ02 | CN.C2.0100 | CN | ME | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Budgeted Units | 2023-09-17: 21548.48; 2023-09-24: 32322.72
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Actual Units | 2023-09-17: 21548.48; 2023-09-24: 32322.72
PCS_PJ02 | CN.C2.0110 | CN | MM | EVSV | Remaining Units
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Budgeted Units | 2023-10-29: 232069.71; 2023-11-05: 406122; 2023-11-12: 406122; 2023-11-19: 406122; 2023-11-26: 174052.29
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | EVSV | Remaining Units | 2023-10-29: 232069.71; 2023-11-05: 406122; 2023-11-12: 406122; 2023-11-19: 406122; 2023-11-26: 174052.29
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Actual Units | 2023-03-05: 373456.16; 2023-03-12: 373456.16; 2023-03-19: 320105.28
PCS_PJ02 | CN.C3.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Budgeted Units | 2023-06-11: 96698.48; 2023-06-18: 580190.88; 2023-07-02: 96698.48; 2023-07-09: 193396.96
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Actual Units | 2023-06-11: 138140.69; 2023-06-18: 828844.11
PCS_PJ02 | CN.C3.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Actual Units | 2023-03-19: 10003.3; 2023-03-26: 70023.1; 2023-04-02: 70023.1; 2023-04-09: 10003.3
PCS_PJ02 | CN.C3.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 79192.73; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 554349.13; 2023-05-28: 158385.47
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Actual Units | 2023-04-30: 79192.73; 2023-05-07: 554349.13; 2023-05-14: 554349.13; 2023-05-21: 554349.13; 2023-05-28: 158385.47
PCS_PJ02 | CN.C3.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Budgeted Units | 2023-05-28: 580816.22; 2023-06-04: 813142.71; 2023-06-11: 696979.47
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Actual Units | 2023-05-28: 491985.51; 2023-06-04: 860974.64; 2023-06-11: 737978.26
PCS_PJ02 | CN.C3.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Budgeted Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Actual Units | 2023-09-24: 629677.09; 2023-10-01: 881547.93; 2023-10-08: 881547.93; 2023-10-15: 377806.25
PCS_PJ02 | CN.C3.0060 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Budgeted Units | 2023-10-15: 171986.53; 2023-10-22: 300976.42; 2023-10-29: 300976.42; 2023-11-05: 42996.63
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Actual Units | 2023-10-15: 70023.09; 2023-10-22: 122540.4; 2023-10-29: 52517.31
PCS_PJ02 | CN.C3.0070 | CN | CV | EVSV | Remaining Units | 2023-10-29: 571855.2
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Budgeted Units | 2023-08-13: 952313.52; 2023-08-20: 2222064.88; 2023-08-27: 2222064.88; 2023-09-03: 2222064.88; 2023-09-10: 1904627.04
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Actual Units | 2023-08-27: 2222064.88; 2023-09-03: 2222064.88; 2023-09-10: 2222064.88; 2023-09-17: 2222064.88; 2023-09-24: 634875.68
PCS_PJ02 | CN.C3.0080 | CN | MC | EVSV | Remaining Units
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Budgeted Units | 2023-11-12: 1923759.93; 2023-11-19: 2244386.58; 2023-11-26: 2244386.58; 2023-12-03: 641253.31
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | EVSV | Remaining Units | 2023-11-12: 1923759.93; 2023-11-19: 2244386.58; 2023-11-26: 2244386.58; 2023-12-03: 641253.31
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Budgeted Units | 2023-10-29: 8894.49; 2023-11-05: 62261.42; 2023-11-12: 8894.49
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | EVSV | Remaining Units | 2023-10-29: 8894.49; 2023-11-05: 62261.42; 2023-11-12: 8894.49
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Budgeted Units | 2023-11-12: 32322.72; 2023-11-19: 21548.48
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | EVSV | Remaining Units | 2023-11-12: 32322.72; 2023-11-19: 21548.48
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Budgeted Units | 2023-12-03: 290087.14; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 406122; 2023-12-31: 116034.86
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | EVSV | Remaining Units | 2023-12-03: 290087.14; 2023-12-10: 406122; 2023-12-17: 406122; 2023-12-24: 406122; 2023-12-31: 116034.86
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Budgeted Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Actual Units | 2023-03-19: 53350.88; 2023-03-26: 373456.16; 2023-04-02: 373456.16; 2023-04-09: 266754.4
PCS_PJ02 | CN.C4.0010 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Budgeted Units | 2023-07-16: 483492.4; 2023-07-23: 483492.4
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Actual Units | 2023-07-16: 345351.71; 2023-07-23: 483492.4; 2023-07-30: 138140.69
PCS_PJ02 | CN.C4.0020 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Budgeted Units | 2023-04-30: 60019.8; 2023-05-07: 70023.1; 2023-05-14: 30009.9
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Actual Units | 2023-04-30: 60019.8; 2023-05-07: 70023.1; 2023-05-14: 30009.9
PCS_PJ02 | CN.C4.0030 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Budgeted Units | 2023-05-28: 395963.67; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 395963.67
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Actual Units | 2023-05-28: 395963.67; 2023-06-04: 554349.13; 2023-06-11: 554349.13; 2023-06-18: 395963.67
PCS_PJ02 | CN.C4.0040 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Budgeted Units | 2023-06-18: 116163.24; 2023-07-02: 116163.24; 2023-07-09: 813142.71; 2023-07-16: 813142.71; 2023-07-23: 232326.49
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Actual Units | 2023-06-18: 190085.31; 2023-07-02: 190085.31; 2023-07-09: 1330597.16; 2023-07-16: 380170.62
PCS_PJ02 | CN.C4.0050 | CN | CV | EVSV | Remaining Units
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Budgeted Units | 2023-10-29: 251870.84; 2023-11-05: 881547.93; 2023-11-12: 881547.93; 2023-11-19: 755612.51
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | EVSV | Remaining Units | 2023-10-29: 251870.84; 2023-11-05: 881547.93; 2023-11-12: 881547.93; 2023-11-19: 755612.51
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Budgeted Units | 2023-11-19: 42996.63; 2023-11-26: 300976.42; 2023-12-03: 300976.42; 2023-12-10: 171986.53
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | EVSV | Remaining Units | 2023-11-19: 42996.63; 2023-11-26: 300976.42; 2023-12-03: 300976.42; 2023-12-10: 171986.53
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Budgeted Units | 2023-09-24: 1587189.2; 2023-10-01: 2222064.88; 2023-10-08: 2222064.88; 2023-10-15: 2222064.88; 2023-10-22: 1269751.36
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Actual Units | 2023-09-24: 1190391.88; 2023-10-01: 1666548.63; 2023-10-08: 1666548.63; 2023-10-15: 1666548.63; 2023-10-22: 1666548.63; 2023-10-29: 714235.13
PCS_PJ02 | CN.C4.0080 | CN | MC | EVSV | Remaining Units | 2023-10-29: 952313.7
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Budgeted Units | 2023-12-10: 961879.96; 2023-12-17: 2244386.58; 2023-12-24: 2244386.58; 2023-12-31: 1603133.27
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | EVSV | Remaining Units | 2023-12-10: 961879.96; 2023-12-17: 2244386.58; 2023-12-24: 2244386.58; 2023-12-31: 1603133.27
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Budgeted Units | 2023-12-03: 44472.44; 2023-12-10: 35577.96
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | EVSV | Remaining Units | 2023-12-03: 44472.44; 2023-12-10: 35577.96
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Budgeted Units | 2023-12-10: 16161.36; 2023-12-17: 37709.84
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | EVSV | Remaining Units | 2023-12-10: 16161.36; 2023-12-17: 37709.84
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Budgeted Units | 2023-12-31: 116034.86; 2024-01-07: 406122; 2024-01-14: 406122; 2024-01-21: 406122; 2024-01-28: 290087.14
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | EVSV | Remaining Units | 2023-12-31: 116034.86; 2024-01-07: 406122; 2024-01-14: 406122; 2024-01-21: 406122; 2024-01-28: 290087.14
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C1.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C1.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C1.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C1.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C2.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C2.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C2.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C2.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C3.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | EVSV | Remaining Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Budgeted Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | EVSV | Remaining Units
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Budgeted Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Actual Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.GE.0010 | EN | GR | WSSV | Remaining Units
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Budgeted Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Actual Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.GE.0020 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Budgeted Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Actual Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.GE.0030 | EN | CP | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Actual Units | 2023-01-01: 786540.8
PCS_PJ02 | EN.C1.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Actual Units | 2023-01-01: 674177.83; 2023-01-08: 112362.97
PCS_PJ02 | EN.C1.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-08: 589905.6; 2023-01-15: 196635.2
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Actual Units | 2023-01-08: 589905.6; 2023-01-15: 196635.2
PCS_PJ02 | EN.C1.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 131090.13; 2023-01-08: 655450.67
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Actual Units | 2023-01-01: 131090.13; 2023-01-08: 655450.67
PCS_PJ02 | EN.C1.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 561814.86; 2023-01-22: 224725.94
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Actual Units | 2023-01-15: 561814.86; 2023-01-22: 224725.94
PCS_PJ02 | EN.C1.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 327725.33; 2023-01-29: 458815.47
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Actual Units | 2023-01-22: 327725.33; 2023-01-29: 458815.47
PCS_PJ02 | EN.C1.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Actual Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Actual Units | 2023-01-08: 314616.32; 2023-01-15: 471924.48
PCS_PJ02 | EN.C1.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-01: 157308.16; 2023-01-08: 629232.64
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Actual Units | 2023-01-01: 157308.16; 2023-01-08: 629232.64
PCS_PJ02 | EN.C2.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-08: 674177.83; 2023-01-15: 112362.97
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Actual Units | 2023-01-08: 674177.83; 2023-01-15: 112362.97
PCS_PJ02 | EN.C2.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-15: 491588; 2023-01-22: 294952.8
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Actual Units | 2023-01-15: 491588; 2023-01-22: 294952.8
PCS_PJ02 | EN.C2.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 262180.27; 2023-01-15: 524360.53
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Actual Units | 2023-01-08: 262180.27; 2023-01-15: 524360.53
PCS_PJ02 | EN.C2.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 449451.89; 2023-01-29: 337088.91
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Actual Units | 2023-01-22: 449451.89; 2023-01-29: 337088.91
PCS_PJ02 | EN.C2.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 262180.27; 2023-02-05: 458815.47; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Actual Units | 2023-01-29: 262180.27; 2023-02-05: 458815.47; 2023-02-12: 65545.07
PCS_PJ02 | EN.C2.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Actual Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Actual Units | 2023-01-15: 471924.48; 2023-01-22: 314616.32
PCS_PJ02 | EN.C2.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Actual Units | 2023-01-08: 471924.48; 2023-01-15: 314616.32
PCS_PJ02 | EN.C3.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-15: 674177.83; 2023-01-22: 112362.97
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Actual Units | 2023-01-15: 674177.83; 2023-01-22: 112362.97
PCS_PJ02 | EN.C3.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-22: 393270.4; 2023-01-29: 393270.4
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Actual Units | 2023-01-22: 393270.4; 2023-01-29: 393270.4
PCS_PJ02 | EN.C3.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 393270.4; 2023-01-22: 393270.4
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Actual Units | 2023-01-15: 393270.4; 2023-01-22: 393270.4
PCS_PJ02 | EN.C3.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Budgeted Units | 2023-01-29: 337088.91; 2023-02-05: 449451.89
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Actual Units | 2023-01-29: 337088.91; 2023-02-05: 449451.89
PCS_PJ02 | EN.C3.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 196635.2; 2023-02-12: 458815.47; 2023-02-19: 131090.13
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Actual Units | 2023-02-05: 196635.2; 2023-02-12: 458815.47; 2023-02-19: 131090.13
PCS_PJ02 | EN.C3.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Actual Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Actual Units | 2023-01-22: 629232.64; 2023-01-29: 157308.16
PCS_PJ02 | EN.C3.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Budgeted Units | 2023-01-15: 786540.8
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Actual Units | 2023-01-15: 786540.8
PCS_PJ02 | EN.C4.0010 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Budgeted Units | 2023-01-22: 674177.83; 2023-01-29: 112362.97
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Actual Units | 2023-01-22: 674177.83; 2023-01-29: 112362.97
PCS_PJ02 | EN.C4.0020 | EN | MC | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Budgeted Units | 2023-01-29: 294952.8; 2023-02-05: 491588
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Actual Units | 2023-01-29: 294952.8; 2023-02-05: 491588
PCS_PJ02 | EN.C4.0030 | EN | EL | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Budgeted Units | 2023-01-22: 524360.53; 2023-01-29: 262180.27
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Actual Units | 2023-01-22: 524360.53; 2023-01-29: 262180.27
PCS_PJ02 | EN.C4.0040 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Budgeted Units | 2023-02-05: 224725.94; 2023-02-12: 561814.86
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Actual Units | 2023-02-05: 224725.94; 2023-02-12: 561814.86
PCS_PJ02 | EN.C4.0050 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Budgeted Units | 2023-02-12: 131090.13; 2023-02-19: 458815.47; 2023-02-26: 196635.2
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Actual Units | 2023-02-12: 131090.13; 2023-02-19: 458815.47; 2023-02-26: 196635.2
PCS_PJ02 | EN.C4.0060 | EN | CV | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Budgeted Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Actual Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0070 | EN | ME | WSSV | Remaining Units
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Budgeted Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Actual Units | 2023-01-29: 786540.8
PCS_PJ02 | EN.C4.0080 | EN | MM | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Budgeted Units | 2023-03-19: 3042474.17; 2023-03-26: 5324329.8; 2023-04-02: 5324329.8; 2023-04-09: 3803092.72
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Actual Units | 2023-03-19: 999670.09; 2023-03-26: 1749422.65; 2023-04-02: 1749422.65; 2023-04-09: 1249587.61; 2023-04-23: 249917.52; 2023-04-30: 1749422.65; 2023-05-07: 1749422.65; 2023-05-14: 1749422.65; 2023-05-21: 1749422.65; 2023-05-28: 1749422.65; 2023-06-04: 1749422.65; 2023-06-11: 999670.09
PCS_PJ02 | PC.GE.0010 | PC | CV | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Budgeted Units | 2023-04-30: 85972.75; 2023-05-07: 601809.25; 2023-05-14: 601809.25; 2023-05-21: 601809.25; 2023-05-28: 601809.25; 2023-06-04: 601809.25; 2023-06-11: 601809.25; 2023-06-18: 515836.5; 2023-07-02: 85972.75; 2023-07-09: 601809.25; 2023-07-16: 257918.25
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Actual Units | 2023-04-30: 73690.93; 2023-05-07: 515836.5; 2023-05-14: 515836.5; 2023-05-21: 515836.5; 2023-05-28: 515836.5; 2023-06-04: 515836.5; 2023-06-11: 515836.5; 2023-06-18: 442145.57; 2023-07-02: 73690.93; 2023-07-09: 515836.5; 2023-07-16: 515836.5; 2023-07-23: 442145.57
PCS_PJ02 | PC.GE.0020 | PC | CV | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Budgeted Units | 2023-01-29: 4008786.53; 2023-02-05: 4676917.61; 2023-02-12: 4676917.61; 2023-02-19: 4676917.61; 2023-02-26: 4676917.61; 2023-03-05: 4676917.61; 2023-03-12: 4676917.61; 2023-03-19: 4676917.61; 2023-03-26: 4676917.61; 2023-04-02: 4676917.61; 2023-04-09: 3340655.44; 2023-04-23: 668131.09; 2023-04-30: 4676917.61; 2023-05-07: 4676917.61; 2023-05-14: 668131.09
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Actual Units | 2023-01-29: 3436102.74; 2023-02-05: 4008786.53; 2023-02-12: 4008786.53; 2023-02-19: 4008786.53; 2023-02-26: 4008786.53; 2023-03-05: 4008786.53; 2023-03-12: 4008786.53; 2023-03-19: 4008786.53; 2023-03-26: 4008786.53; 2023-04-02: 4008786.53; 2023-04-09: 2863418.95; 2023-04-23: 572683.79; 2023-04-30: 4008786.53; 2023-05-07: 4008786.53; 2023-05-14: 4008786.53; 2023-05-21: 4008786.53; 2023-05-28: 1145367.58
PCS_PJ02 | PC.GE.0030 | PC | MC | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Actual Units | 2023-04-09: 1328841.99; 2023-04-23: 442947.33; 2023-04-30: 3100631.31; 2023-05-07: 3100631.31; 2023-05-14: 3100631.31; 2023-05-21: 3100631.31; 2023-05-28: 3100631.31; 2023-06-04: 3100631.31; 2023-06-11: 3100631.31; 2023-06-18: 2657683.98; 2023-07-02: 442947.33; 2023-07-09: 3100631.31; 2023-07-16: 3100631.31; 2023-07-23: 3100631.31; 2023-07-30: 3100631.31; 2023-08-06: 885894.66
PCS_PJ02 | PC.GE.0040 | PC | EL | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Budgeted Units | 2023-04-09: 233718.15; 2023-04-23: 77906.05; 2023-04-30: 545342.35; 2023-05-07: 545342.35; 2023-05-14: 545342.35; 2023-05-21: 545342.35; 2023-05-28: 545342.35; 2023-06-04: 545342.35; 2023-06-11: 545342.35; 2023-06-18: 467436.3; 2023-07-02: 77906.05
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Actual Units | 2023-04-09: 175288.61; 2023-04-23: 58429.54; 2023-04-30: 409006.76; 2023-05-07: 409006.76; 2023-05-14: 409006.76; 2023-05-21: 409006.76; 2023-05-28: 409006.76; 2023-06-04: 409006.76; 2023-06-11: 409006.76; 2023-06-18: 350577.23; 2023-07-02: 58429.54; 2023-07-09: 409006.76; 2023-07-16: 409006.76; 2023-07-23: 350577.22
PCS_PJ02 | PC.GE.0050 | PC | EL | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Budgeted Units | 2023-06-11: 50546.08; 2023-06-18: 101092.16; 2023-07-02: 16848.69; 2023-07-09: 117940.85; 2023-07-16: 117940.85; 2023-07-23: 101092.16
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Actual Units | 2023-06-11: 24858.73; 2023-06-18: 49717.46; 2023-07-02: 8286.24; 2023-07-09: 58003.7; 2023-07-16: 58003.7; 2023-07-23: 58003.7; 2023-07-30: 58003.7; 2023-08-06: 58003.7; 2023-08-13: 58003.7; 2023-08-20: 58003.7; 2023-08-27: 16572.49
PCS_PJ02 | PC.GE.0060 | PC | ME | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Budgeted Units | 2023-06-11: 34015.73; 2023-06-18: 68031.46; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.46
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Actual Units | 2023-06-11: 34015.73; 2023-06-18: 68031.46; 2023-07-02: 11338.58; 2023-07-09: 79370.04; 2023-07-16: 79370.04; 2023-07-23: 68031.46
PCS_PJ02 | PC.GE.0070 | PC | MM | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Budgeted Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Actual Units | 2023-03-19: 371608.62; 2023-03-26: 433543.38; 2023-04-02: 433543.38; 2023-04-09: 309673.85; 2023-04-23: 61934.77; 2023-04-30: 433543.38; 2023-05-07: 433543.38; 2023-05-14: 433543.38; 2023-05-21: 433543.38; 2023-05-28: 433543.38; 2023-06-04: 433543.38; 2023-06-11: 433543.38; 2023-06-18: 371608.62; 2023-07-02: 61934.77; 2023-07-09: 433543.38; 2023-07-16: 433543.38; 2023-07-23: 433543.38; 2023-07-30: 433543.38; 2023-08-06: 433543.38; 2023-08-13: 185804.31
PCS_PJ02 | PC.GE.0080 | PC | CP | WSSV | Remaining Units
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Budgeted Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Actual Units | 2023-04-09: 94177.01; 2023-04-23: 31392.34; 2023-04-30: 219746.35; 2023-05-07: 219746.35; 2023-05-14: 219746.35; 2023-05-21: 219746.35; 2023-05-28: 219746.35; 2023-06-04: 219746.35; 2023-06-11: 219746.35; 2023-06-18: 188354.01; 2023-07-02: 31392.34; 2023-07-09: 219746.35; 2023-07-16: 219746.35; 2023-07-23: 219746.35; 2023-07-30: 219746.35; 2023-08-06: 62784.67
PCS_PJ02 | PC.GE.0090 | PC | CP | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Budgeted Units | 2023-01-22: 226741.33; 2023-01-29: 317437.86; 2023-02-05: 317437.86; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Actual Units | 2023-01-22: 226741.33; 2023-01-29: 317437.86; 2023-02-05: 317437.86; 2023-02-12: 45348.26
PCS_PJ02 | CN.C1.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 493162.38; 2023-05-07: 328774.92
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Actual Units | 2023-04-30: 164387.46; 2023-05-07: 575356.11; 2023-05-14: 82193.73
PCS_PJ02 | CN.C1.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Actual Units | 2023-02-12: 51016.8; 2023-02-19: 59519.6; 2023-02-26: 25508.4
PCS_PJ02 | CN.C1.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Budgeted Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Actual Units | 2023-02-26: 269255.32; 2023-03-05: 471196.8; 2023-03-12: 471196.8; 2023-03-19: 403882.98
PCS_PJ02 | CN.C1.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 98738.76; 2023-03-26: 691171.33; 2023-04-02: 691171.33; 2023-04-09: 296216.28
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Actual Units | 2023-03-19: 88864.89; 2023-03-26: 622054.2; 2023-04-02: 622054.2; 2023-04-09: 444324.43
PCS_PJ02 | CN.C1.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 535225.45; 2023-07-23: 749315.64; 2023-07-30: 749315.64; 2023-08-06: 321135.27
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Actual Units | 2023-07-16: 535225.45; 2023-07-23: 749315.64; 2023-07-30: 749315.64; 2023-08-06: 321135.27
PCS_PJ02 | CN.C1.0060 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Budgeted Units | 2023-08-06: 146188.48; 2023-08-13: 255829.85; 2023-08-20: 255829.85; 2023-08-27: 36547.12
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Actual Units | 2023-08-06: 146188.48; 2023-08-13: 255829.85; 2023-08-20: 255829.85; 2023-08-27: 36547.12
PCS_PJ02 | CN.C1.0070 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Budgeted Units | 2023-05-28: 1349110.85; 2023-06-04: 1888755.19; 2023-06-11: 1888755.19; 2023-06-18: 1618933.02; 2023-07-02: 269822.17; 2023-07-09: 1079288.68
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Actual Units | 2023-05-28: 1156380.73; 2023-06-04: 1618933.02; 2023-06-11: 1618933.02; 2023-06-18: 1387656.87; 2023-07-02: 231276.15; 2023-07-09: 1618933.02; 2023-07-16: 462552.29
PCS_PJ02 | CN.C1.0080 | CN | MC | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Budgeted Units | 2023-08-27: 545065.31; 2023-09-03: 1907728.58; 2023-09-10: 1907728.58; 2023-09-17: 1635195.93
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Actual Units | 2023-08-27: 545065.31; 2023-09-03: 1907728.58; 2023-09-10: 1907728.58; 2023-09-17: 1635195.93
PCS_PJ02 | CN.C1.0090 | CN | EL | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Budgeted Units | 2023-08-27: 15120.62; 2023-09-03: 52922.18
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Actual Units | 2023-08-27: 15120.62; 2023-09-03: 52922.18
PCS_PJ02 | CN.C1.0100 | CN | ME | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Budgeted Units | 2023-09-10: 32053.28; 2023-09-17: 13737.12
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Actual Units | 2023-09-10: 32053.28; 2023-09-17: 13737.12
PCS_PJ02 | CN.C1.0110 | CN | MM | WSSV | Remaining Units
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Budgeted Units | 2023-09-17: 49314.82; 2023-09-24: 345203.75; 2023-10-01: 345203.75; 2023-10-08: 345203.75; 2023-10-15: 295888.93
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Actual Units | 2023-09-17: 30347.58; 2023-09-24: 212433.08; 2023-10-01: 212433.08; 2023-10-08: 212433.08; 2023-10-15: 212433.08; 2023-10-22: 212433.08; 2023-10-29: 91042.75
PCS_PJ02 | CN.C1.0120 | CN | CP | WSSV | Remaining Units | 2023-10-29: 197259.29
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Budgeted Units | 2023-02-12: 272089.59; 2023-02-19: 317437.86; 2023-02-26: 317437.86
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Actual Units | 2023-02-12: 272089.59; 2023-02-19: 317437.86; 2023-02-26: 317437.86
PCS_PJ02 | CN.C2.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Budgeted Units | 2023-07-02: 82193.73; 2023-07-09: 575356.11; 2023-07-16: 164387.46
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Actual Units | 2023-07-02: 82193.73; 2023-07-09: 575356.11; 2023-07-16: 164387.46
PCS_PJ02 | CN.C2.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Actual Units | 2023-03-05: 59519.6; 2023-03-12: 59519.6; 2023-03-19: 17005.6
PCS_PJ02 | CN.C2.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 67313.83; 2023-03-26: 471196.8; 2023-04-02: 471196.8; 2023-04-09: 336569.15; 2023-04-23: 67313.83; 2023-04-30: 201941.49
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Actual Units | 2023-03-19: 59834.51; 2023-03-26: 418841.6; 2023-04-02: 418841.6; 2023-04-09: 299172.57; 2023-04-23: 59834.51; 2023-04-30: 359007.09
PCS_PJ02 | CN.C2.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 98738.76; 2023-05-07: 691171.33; 2023-05-14: 691171.33; 2023-05-21: 296216.28
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Actual Units | 2023-04-30: 71091.91; 2023-05-07: 497643.36; 2023-05-14: 497643.36; 2023-05-21: 497643.36; 2023-05-28: 213275.72
PCS_PJ02 | CN.C2.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Budgeted Units | 2023-08-13: 321135.27; 2023-08-20: 749315.64; 2023-08-27: 749315.64; 2023-09-03: 535225.45
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Actual Units | 2023-08-13: 470998.4; 2023-08-20: 1098996.27; 2023-08-27: 784997.33
PCS_PJ02 | CN.C2.0060 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Budgeted Units | 2023-08-27: 73094.24; 2023-09-03: 255829.85; 2023-09-10: 255829.85; 2023-09-17: 109641.36
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Actual Units | 2023-08-27: 73094.24; 2023-09-03: 255829.85; 2023-09-10: 255829.85; 2023-09-17: 109641.36
PCS_PJ02 | CN.C2.0070 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Budgeted Units | 2023-07-16: 1349110.85; 2023-07-23: 1888755.19; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1079288.68
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Actual Units | 2023-07-16: 1349110.85; 2023-07-23: 1888755.19; 2023-07-30: 1888755.19; 2023-08-06: 1888755.19; 2023-08-13: 1079288.68
PCS_PJ02 | CN.C2.0080 | CN | MC | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Budgeted Units | 2023-09-17: 1090130.62; 2023-09-24: 1907728.58; 2023-10-01: 1907728.58; 2023-10-08: 1090130.62
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Actual Units | 2023-09-17: 1090130.62; 2023-09-24: 1907728.58; 2023-10-01: 1907728.58; 2023-10-08: 1090130.62
PCS_PJ02 | CN.C2.0090 | CN | EL | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Budgeted Units | 2023-09-10: 45361.87; 2023-09-17: 22680.93
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Actual Units | 2023-09-10: 45361.87; 2023-09-17: 22680.93
PCS_PJ02 | CN.C2.0100 | CN | ME | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Budgeted Units | 2023-09-17: 18316.16; 2023-09-24: 27474.24
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Actual Units | 2023-09-17: 18316.16; 2023-09-24: 27474.24
PCS_PJ02 | CN.C2.0110 | CN | MM | WSSV | Remaining Units
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Budgeted Units | 2023-10-29: 197259.29; 2023-11-05: 345203.75; 2023-11-12: 345203.75; 2023-11-19: 345203.75; 2023-11-26: 147944.46
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C2.0120 | CN | CP | WSSV | Remaining Units | 2023-10-29: 197259.29; 2023-11-05: 345203.75; 2023-11-12: 345203.75; 2023-11-19: 345203.75; 2023-11-26: 147944.46
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-05: 317437.86; 2023-03-12: 317437.86; 2023-03-19: 272089.59
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Actual Units | 2023-03-05: 317437.86; 2023-03-12: 317437.86; 2023-03-19: 272089.59
PCS_PJ02 | CN.C3.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Budgeted Units | 2023-06-11: 82193.73; 2023-06-18: 493162.38; 2023-07-02: 82193.73; 2023-07-09: 164387.46
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Actual Units | 2023-06-11: 117419.61; 2023-06-18: 704517.69
PCS_PJ02 | CN.C3.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Actual Units | 2023-03-19: 8502.8; 2023-03-26: 59519.6; 2023-04-02: 59519.6; 2023-04-09: 8502.8
PCS_PJ02 | CN.C3.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 67313.83; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 471196.8; 2023-05-28: 134627.66
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Actual Units | 2023-04-30: 67313.83; 2023-05-07: 471196.8; 2023-05-14: 471196.8; 2023-05-21: 471196.8; 2023-05-28: 134627.66
PCS_PJ02 | CN.C3.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Budgeted Units | 2023-05-28: 493693.81; 2023-06-04: 691171.33; 2023-06-11: 592432.57
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Actual Units | 2023-05-28: 418187.69; 2023-06-04: 731828.46; 2023-06-11: 627281.54
PCS_PJ02 | CN.C3.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Budgeted Units | 2023-09-24: 535225.45; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.27
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Actual Units | 2023-09-24: 535225.45; 2023-10-01: 749315.64; 2023-10-08: 749315.64; 2023-10-15: 321135.27
PCS_PJ02 | CN.C3.0060 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Budgeted Units | 2023-10-15: 146188.48; 2023-10-22: 255829.85; 2023-10-29: 255829.85; 2023-11-05: 36547.12
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Actual Units | 2023-10-15: 73094.24; 2023-10-22: 127914.92; 2023-10-29: 54820.68
PCS_PJ02 | CN.C3.0070 | CN | CV | WSSV | Remaining Units | 2023-10-29: 438565.45
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Budgeted Units | 2023-08-13: 809466.51; 2023-08-20: 1888755.19; 2023-08-27: 1888755.19; 2023-09-03: 1888755.19; 2023-09-10: 1618933.02
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Actual Units | 2023-08-27: 1888755.19; 2023-09-03: 1888755.19; 2023-09-10: 1888755.19; 2023-09-17: 1888755.19; 2023-09-24: 539644.34
PCS_PJ02 | CN.C3.0080 | CN | MC | WSSV | Remaining Units
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Budgeted Units | 2023-11-12: 1635195.93; 2023-11-19: 1907728.58; 2023-11-26: 1907728.58; 2023-12-03: 545065.31
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C3.0090 | CN | EL | WSSV | Remaining Units | 2023-11-12: 1635195.93; 2023-11-19: 1907728.58; 2023-11-26: 1907728.58; 2023-12-03: 545065.31
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Budgeted Units | 2023-10-29: 7560.31; 2023-11-05: 52922.18; 2023-11-12: 7560.31
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C3.0100 | CN | ME | WSSV | Remaining Units | 2023-10-29: 7560.31; 2023-11-05: 52922.18; 2023-11-12: 7560.31
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Budgeted Units | 2023-11-12: 27474.24; 2023-11-19: 18316.16
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C3.0110 | CN | MM | WSSV | Remaining Units | 2023-11-12: 27474.24; 2023-11-19: 18316.16
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Budgeted Units | 2023-12-03: 246574.11; 2023-12-10: 345203.75; 2023-12-17: 345203.75; 2023-12-24: 345203.75; 2023-12-31: 98629.64
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C3.0120 | CN | CP | WSSV | Remaining Units | 2023-12-03: 246574.11; 2023-12-10: 345203.75; 2023-12-17: 345203.75; 2023-12-24: 345203.75; 2023-12-31: 98629.64
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Budgeted Units | 2023-03-19: 45348.27; 2023-03-26: 317437.86; 2023-04-02: 317437.86; 2023-04-09: 226741.33
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Actual Units | 2023-03-19: 45348.27; 2023-03-26: 317437.86; 2023-04-02: 317437.86; 2023-04-09: 226741.33
PCS_PJ02 | CN.C4.0010 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Budgeted Units | 2023-07-16: 410968.65; 2023-07-23: 410968.65
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Actual Units | 2023-07-16: 293549.04; 2023-07-23: 410968.65; 2023-07-30: 117419.61
PCS_PJ02 | CN.C4.0020 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Budgeted Units | 2023-04-30: 51016.8; 2023-05-07: 59519.6; 2023-05-14: 25508.4
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Actual Units | 2023-04-30: 51016.8; 2023-05-07: 59519.6; 2023-05-14: 25508.4
PCS_PJ02 | CN.C4.0030 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Budgeted Units | 2023-05-28: 336569.15; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 336569.15
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Actual Units | 2023-05-28: 336569.15; 2023-06-04: 471196.8; 2023-06-11: 471196.8; 2023-06-18: 336569.15
PCS_PJ02 | CN.C4.0040 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Budgeted Units | 2023-06-18: 98738.76; 2023-07-02: 98738.76; 2023-07-09: 691171.33; 2023-07-16: 691171.33; 2023-07-23: 197477.52
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Actual Units | 2023-06-18: 161572.52; 2023-07-02: 161572.52; 2023-07-09: 1131007.63; 2023-07-16: 323145.04
PCS_PJ02 | CN.C4.0050 | CN | CV | WSSV | Remaining Units
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Budgeted Units | 2023-10-29: 214090.18; 2023-11-05: 749315.64; 2023-11-12: 749315.64; 2023-11-19: 642270.55
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0060 | CN | CV | WSSV | Remaining Units | 2023-10-29: 214090.18; 2023-11-05: 749315.64; 2023-11-12: 749315.64; 2023-11-19: 642270.55
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Budgeted Units | 2023-11-19: 36547.12; 2023-11-26: 255829.85; 2023-12-03: 255829.85; 2023-12-10: 146188.48
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Actual Units
PCS_PJ02 | CN.C4.0070 | CN | CV | WSSV | Remaining Units | 2023-11-19: 36547.12; 2023-11-26: 255829.85; 2023-12-03: 255829.85; 2023-12-10: 146188.48
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Budgeted Units | 2023-09-24: 1349110.85; 2023-10-01: 1888755.19; 2023-10-08: 1888755.19; 2023-10-15: 1888755.19; 2023-10-22: 1079288.68
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Actual Units | 2023-09-24: 1049308.44; 2023-10-01: 1469031.81; 2023-10-08: 1469031.81; 2023-10-15: 1469031.81; 2023-10-22: 1469031.81; 2023-10-29: 629585.06
PCS_PJ02 | CN.C4.0080 | CN | MC | WSSV | Remaining Units | 2023-10-29: 539644.34
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Budgeted Units | 2023-12-10: 817597.96; 2023-12-17: 1907728.58; 2023-12-24: 1907728.58; 2023-12-31: 1362663.27
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Actual Units
PCS_PJ02 | CN.C4.0090 | CN | EL | WSSV | Remaining Units | 2023-12-10: 817597.96; 2023-12-17: 1907728.58; 2023-12-24: 1907728.58; 2023-12-31: 1362663.27
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Budgeted Units | 2023-12-03: 37801.56; 2023-12-10: 30241.24
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Actual Units
PCS_PJ02 | CN.C4.0100 | CN | ME | WSSV | Remaining Units | 2023-12-03: 37801.56; 2023-12-10: 30241.24
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Budgeted Units | 2023-12-10: 13737.12; 2023-12-17: 32053.28
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Actual Units
PCS_PJ02 | CN.C4.0110 | CN | MM | WSSV | Remaining Units | 2023-12-10: 13737.12; 2023-12-17: 32053.28
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Budgeted Units | 2023-12-31: 98629.64; 2024-01-07: 345203.75; 2024-01-14: 345203.75; 2024-01-21: 345203.75; 2024-01-28: 246574.11
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Actual Units
PCS_PJ02 | CN.C4.0120 | CN | CP | WSSV | Remaining Units | 2023-12-31: 98629.64; 2024-01-07: 345203.75; 2024-01-14: 345203.75; 2024-01-21: 345203.75; 2024-01-28: 246574.11
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Budgeted Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Actual Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C1.0010 | TS | MC | WSSV | Remaining Units
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Budgeted Units | 2023-09-17: 114703.87; 2023-09-24: 573519.33
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Actual Units | 2023-09-17: 114703.87; 2023-09-24: 573519.33
PCS_PJ02 | TS.C1.0020 | TS | EL | WSSV | Remaining Units
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Budgeted Units | 2023-09-10: 688223.2
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Actual Units | 2023-09-10: 688223.2
PCS_PJ02 | TS.C1.0030 | TS | ME | WSSV | Remaining Units
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Budgeted Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Actual Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C1.0040 | TS | MM | WSSV | Remaining Units
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Budgeted Units | 2023-11-05: 688223.2
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C1.0050 | TS | CP | WSSV | Remaining Units | 2023-11-05: 688223.2
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Budgeted Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Actual Units | 2023-08-27: 229407.73; 2023-09-03: 458815.47
PCS_PJ02 | TS.C2.0010 | TS | MC | WSSV | Remaining Units
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Budgeted Units | 2023-10-08: 344111.6; 2023-10-15: 344111.6
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Actual Units | 2023-10-08: 344111.6; 2023-10-15: 344111.6
PCS_PJ02 | TS.C2.0020 | TS | EL | WSSV | Remaining Units
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Budgeted Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Actual Units | 2023-09-17: 458815.47; 2023-09-24: 229407.73
PCS_PJ02 | TS.C2.0030 | TS | ME | WSSV | Remaining Units
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Budgeted Units | 2023-09-24: 114703.87; 2023-10-01: 573519.33
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Actual Units | 2023-09-24: 114703.87; 2023-10-01: 573519.33
PCS_PJ02 | TS.C2.0040 | TS | MM | WSSV | Remaining Units
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Budgeted Units | 2023-11-26: 458815.47; 2023-12-03: 229407.73
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C2.0050 | TS | CP | WSSV | Remaining Units | 2023-11-26: 458815.47; 2023-12-03: 229407.73
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Budgeted Units | 2023-09-24: 573519.33; 2023-10-01: 114703.87
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Actual Units | 2023-09-24: 573519.33; 2023-10-01: 114703.87
PCS_PJ02 | TS.C3.0010 | TS | MC | WSSV | Remaining Units
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Budgeted Units | 2023-12-03: 573519.33; 2023-12-10: 114703.87
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C3.0020 | TS | EL | WSSV | Remaining Units | 2023-12-03: 573519.33; 2023-12-10: 114703.87
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Budgeted Units | 2023-11-12: 688223.2
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C3.0030 | TS | ME | WSSV | Remaining Units | 2023-11-12: 688223.2
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Budgeted Units | 2023-11-19: 344111.6; 2023-11-26: 344111.6
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C3.0040 | TS | MM | WSSV | Remaining Units | 2023-11-19: 344111.6; 2023-11-26: 344111.6
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Budgeted Units | 2023-12-31: 573519.33; 2024-01-07: 114703.87
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C3.0050 | TS | CP | WSSV | Remaining Units | 2023-12-31: 573519.33; 2024-01-07: 114703.87
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Budgeted Units | 2023-10-29: 229407.73; 2023-11-05: 458815.47
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Actual Units
PCS_PJ02 | TS.C4.0010 | TS | MC | WSSV | Remaining Units | 2023-10-29: 229407.73; 2023-11-05: 458815.47
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Budgeted Units | 2023-12-31: 229407.73; 2024-01-07: 458815.47
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Actual Units
PCS_PJ02 | TS.C4.0020 | TS | EL | WSSV | Remaining Units | 2023-12-31: 229407.73; 2024-01-07: 458815.47
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Budgeted Units | 2023-12-10: 344111.6; 2023-12-17: 344111.6
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Actual Units
PCS_PJ02 | TS.C4.0030 | TS | ME | WSSV | Remaining Units | 2023-12-10: 344111.6; 2023-12-17: 344111.6
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Budgeted Units | 2023-12-24: 688223.2
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Actual Units
PCS_PJ02 | TS.C4.0040 | TS | MM | WSSV | Remaining Units | 2023-12-24: 688223.2
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Budgeted Units | 2024-01-28: 229407.73; 2024-02-04: 458815.47
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Actual Units
PCS_PJ02 | TS.C4.0050 | TS | CP | WSSV | Remaining Units | 2024-01-28: 229407.73; 2024-02-04: 458815.47