## Project Plan
Task ID | Task Name | Start Date | End Date | Progress | Status | Spent | Budget | Resources
T1 | Site Prep | 2026-02-28 | 2026-03-15 | 100 | Completed | 120000 | 115000 | A. Kowalski, Excavator
T2 | Foundation laying | 2026-03-16 | 2026-04-09 | 72 | In Progress | 450000 | 500000 | R. Patel, Mixer
T3 | Steel erection | 2026-03-25 | 2026-04-19 | 10 | In Progress | 800000 | 1200000 | M. Okafor, Crane #1, Welders
T4 | Concrete pour | 2026-04-02 | 2026-04-14 | 0 | Not Started | 0 | 400000 | T. Zhang, Pump truck
T5 | Deck surfacing | 2026-04-15 | 2026-04-24 | 0 | Not Started | 0 | 200000 | L. Ferreira
T6 | Railing & safety | 2026-04-25 | 2026-05-04 | 0 | Not Started | 0 | 150000 | K. Ibrahim